## Slide 1: Nutrition Cluster Advocacy
Experiences and lessons Learnt from the Yemen Nutrition Cluster

## Slide 2: Advocacy Strategy Development Process
  Partners identified need to strengthen advocacy during CCPM & later in 2018 HRP development  added advocacy strategy to HRP/cluster workplan
  UNICEF as PoLR agreed to fund
  NCC developed draft TOR, reviewed by the SAG, with clear process and outputs
  NCC hired a consultant to draft strategy (working remotely)
  Initial identification of priorities for advocacy through desk review and interviews

## Slide 3: Advocacy Strategy Development Process
  Online survey to gather views of NC partners on key priorities for advocacy, key stakeholders & opportunities for advocacy
  First draft of Advocacy Strategy developed by consultant, with input from the SAG
  Draft strategy reviewed at the workshop with Cluster partners
  Final version validated with SAG & Cluster partners
  Development of Advocacy Action Plan based on strategy & workshop
  SAG leading on Advocacy Strategy implementation – agreed to add standing agenda item on advocacy to all SAG meetings
 Conducting interviews, online advocacy survey & an advocacy workshop were key steps in ensuring advocacy strategy reflected views of cluster partners and was relevant to their work & priorities

## Slide 4: 2018-2020 Advocacy Strategy objectives
GOAL: To support the implementation of the nutrition cluster strategic objectives in Yemen tackling identified challenges to respond to the nutritional needs of emergency-affected population
ADVOCAY OBJECTIVE 1 : The MoPHP and other nutrition actors in Yemen promote and scale up a comprehensive nutrition package with the prioritization of both treatment and preventive direct specific nutrition interventions
ADVOCACY OBJECTIVE 2 : The Ministry of Planning and International Cooperation (MOPIC), the MoPHP and the Nutrition Cluster work with relevant ministries and clusters, including those working on health, food security, agriculture, fisheries, WASH and education for the inclusion and effective implementation of nutrition-sensitive objectives in relevant government sectoral policies and cluster plans
ADVOCACY OBJECTIVE 3 : Improved national capacities at all levels for nutrition action
 Each objective has associated results, opportunities, milestones, core messages and targets

## Slide 5: Key challenges in the development process - how were they addressed?
No technical expertise on advocacy in country – selection of a consultant with good understanding of both nutrition & advocacy
No possibility for a consultant to travel to Yemen – all work was done remotely, with monthly reports on progress and SAG calls
Lack of time by partners/SAG with other priorities – NCC follow-up and leadership
MoPHP involvement – advocacy by the NCC
SUN Secretariat key partner for advocacy - involvement by the NCC

## Slide 6: Update on implementation
Planned advocacy activity | Timeline | Implementation status
Develop a three year scale up plan, agreed with the partners and MoPHP | Dec 2018 | In pipeline... One of the pilot by the NCCT
Develop PPT CMAM and lobbying by conducting coordination meetings with MoPHP, related UN agencies, partners, and nutrition cluster to scale up CMAM for children U5 and PLW |  | Ongoing - High level meetings have been held with MOPHP including the Minister by the cluster as part of the 2019 HRP and individually by UNICEF and WFP.
Discussions with MoPHP towards full nutrition services to be free of charge, including TFC |  | Done. At least in TFCs supported by WHO and UNICEF all the TFC services are free of charge.
Follow up with SAG and Nutrition Cluster partners to finalize SBC strategy | Sept-Oct | Finalized in December 2018. SBC submitted to the MOPHP for endorsement
Lobbying the MoPHP Nutrition Department to work in coordination with health authorities in the country for endorsement of nutrition and IYCF strategies |  | Done. A number of guidelines including IYCF have been lined up for MOPHP endorsement

## Slide 7: Update on implementation
Planned advocacy activity | Timeline | Implementation status
Lobbying to donors/Humanitarian Coordinator for fundraising efforts to support scale up in line with YHRP | 2018-2020 | This was done considerably as part of the HRP scale up - both WFP and UNICEF and WHO has agreed to scale up nutrition responses including targeting and geographical coverage
Conduct workshops among stakeholders and partners to introduce them to the new incentives guideline to ensure all partners follow it |  | This was done- during the cluster meetings one of the agenda. Discussion are going with MOPHP to develop incentives rates for CHVs
Influence SUN to develop and widely disseminate an advocacy paper on problems and gaps in funding to influence selected donors |  | The paper has not been developed, but there cluster is has established good working relationship with the SUN secretariat- we need to take advantage.

## Slide 8: Next steps and future priorities
Next steps
1. Implementation of the pending activities in the advocacy strategy
2. Optimizing the good working relationship with the MOPHP (there is new leadership) to finalize and endorse a number of pending guidelines
3. Linking emergency and development nutrition activities through the SUN movement secretariat including implementation of nutrition day in Yemen.
4. Workshop to orient stakeholders on breastfeeding legislation and international code of marketing BMS and initiating and scaling up breastmilk substitutes

## Slide 9: Helpful tools and documents
2018 – 2020 Yemen Nutrition Cluster Advocacy Strategy (https://reliefweb.int/report/yemen/yemen-nutrition-cluster-advocacy-strategy-2018-2020)
2018 – 2020 Yemen Nutrition Cluster Advocacy Action Plan
ToR for consultant to develop advocacy strategy
Presentation for the partners’ advocacy workshop
Advocacy Calendar
Advocacy Activities Tracker
Advocacy Impact Reporting Tool