UNICEF UGANDA

AFTER ACTION REVIEW OF UNICEF’S EBOLA VIRUS DISEASE RESPONSE IN UGANDA, SEP 2022 – MARS 2023

DRAFT REPORT

1 May 2023

Executive Summary

The Uganda country office (UCO) conducted an after-action review (AAR) of the Ebola virus disease (EVD) response covering the period of September 2022 - March 2023 to review, document and reflect on UNICEF’s preparedness and response to public health outbreaks in Uganda. The purpose of the AAR was to enable internal reflections, identify and document best practices, gaps and lessons learned from the actual experience, and to identify immediate and longer-term corrective actions to inform future responses. The review process included several components – a staff survey, key informant interviews, data review and analysis and a participatory staff workshop.

The review found that UNICEF responded rapidly to an unexpected, large, and fast-moving public health outbreak, which occurred when the public health system was still recovering from the COVID-19 pandemic. The response was characterized by high flexibility in programming and funding, which enabled a rapid scale up and effectiveness. The response was supported by strong existing partnerships, a high-capacity and flexible workforce and organizational support using innovative solution and institutional EVD knowledge. UCO manoeuvred several parameters, which differed from previous EVD outbreaks, with a clear child right focus lens.

However, the response also encountered challenges and the UCO needs to be better prepared for future public health outbreaks. Firstly, keeping in mind this was the seventh EVD outbreak in Uganda, UNICEF needs to strengthen its preparedness for future public health outbreaks. Secondly, at the beginning of the response, UCO did not respond as “one office” but worked in silos and there is a need to improve the ability to work more horizontal and well-coordinated. Thirdly, there is a need for internal clarity on the daily leadership during an emergency response. Finally, UNICEF’s presence in the field speed up the response but the low government capacity on sub-national level was a bottleneck and slowed down the response. UNICEF needs to advocate for and support the strengthening of the health system on sub-national level. As part of this, UCO needs to emphasize the importance of the humanitarian-development nexus and include resilience components in its everyday development work to build the capacity of the government to respond to future public health emergencies. Furthermore, child protection, protection from sexual exploitation and abuse and education need to be integrated in all public health emergencies on national level.

The AAR will be followed-up by the CMT, EMT and a Theory of Change exercise has been planned.  See below a more detailed summary of the AAR findings:

| SUMMARY OF FINDINGS |  |  |
| --- | --- | --- |
| Area of work | What went well | What can be improved |
| - Are we in the right places at the right times? | - UCO’s existing structure in the field. - UCO’s strong leadership and coordination towards the Government and key stakeholders. - Rapid and timely deployment of staff resulting in timely on-ground presence. | - Clarity/improved internal coordination on roles and responsibilities within the office and towards the field to ensure a more uniform and comprehensive response in the field. - The role of the RC. - Weak coordination structures at government sub-national level needs to be strengthened. |
| - Did we prepare? Is our work planned to meet priorities? | - Structures in place that facilitated immediate support to government partners. - EMT structure in place, re-activation of COVID-19 structures in the field and RCCE EVD response plans speed up the response. - High percentage of staff had experience from previous EVD outbreaks. | - Initial delays in design of response and rollout of critical interventions due to lack of public health emergency plans for most sections. - Initial implementation was done in silos due to limited horizontal integration. - Strengthen the role of the field offices. |
| - Are we child-centered and meeting the greatest needs? | - Early decision to have a child focused response due to higher representation of cases among children guided the overall response throughout the emergency. - Programme effectiveness with high achievements of outputs. | - Lack of ORE funding for needed BEAD interventions; initial lack of allocation of funds for CP/MHPSS - Integration of protection in the response was a challenge due to the absence of dedicated coordination fora for protection. |
| - Are we strategically engaging with the right partners? | - Partnerships with relevant partners were already established. - Capacity building of groups/partners from the whole society (incl. religious, political and community leaders, journalists, traditional healers, boda boda association, private sector and other relevant groups enabled a quick response on all levels in society. | - PCAs with relevant partners should be prepared ahead of an emergency. - Recognition of health workers needs to be improved to encourage ongoing health services during outbreaks. - Government had inadequate staffing for implementation of the response. - Ensure UNICEF knowledge about EVD response is documented and shared. |
| - Are we delivering in the most timely and efficient way? | - Immediate access to internal funding that allowed flexible implementation. - Availability of LTAs for transport, accommodation, safety kits, fuel, payments with cards enabled timely delivery. - Innovative methods of paying partners enable a more efficient implementation. | - Need to include Operations and HR from day one in future emergency response. - Ensure preposition of equipment to ensure staff safety and well-being during public health emergency. |
| - Are we adequately leveraging our most valuable resource, UNICEF personnel? | - Rapid staff scale-up thanks to flexibility among UCO staff members and surge staff. - Rapid scale-up thanks to additional TA and Surge staff. | - The pace of the disease out weighted staffing capacity. - Duty of care was more focused on field staff and not Kampala staff. |

The findings are followed by a programmatic review of the response and an action plan tracker with all recommendations.

After action review report

# Introduction and background

On 20 September 2022, the Government of Uganda declared an outbreak of Ebola Virus Disease (EVD) caused by the Sudan ebolavirus species. The same day, WHO classified the outbreak as a Grade 2 emergency. Overall, 142 confirmed cases (28 children) were reported, of which 55 died (CFR: 39 per cent), including 12 children (CRF: 43 per cent), and 87 recovered. At least 19 healthcare workers were infected, of whom seven died (CFR: 37 per cent). Over 4,000 contacts were followed up for 21 days. In total, nine Ugandan districts were affected by the outbreak: Bunyangabu, Jinja, Kagadi, Kampala, Kassanda, Kyegegwa, Masaka, Mubende, and Wakiso. The outbreak was declared over 11 January 2023 after 42 days had passed without any case reported, since the last case was released from care. UNICEF responded to the outbreak the same day it was declared, and 27 October scaled up the emergency to Level 2 (L2).

## Purpose and Objective

On 21 March 2023, the Uganda country office (UCO) conducted an after-action review (AAR) workshop (Annex A) to reflect on UNICEF’s preparedness and response to the L2 EVD emergency. The purpose of the AAR workshop was to enable internal reflections, identify and document best practices, gaps and lessons learned from the actual experience, and to identify immediate and longer-term corrective actions to inform future public health emergencies. The review process included several components – a staff survey, key informant interviews, data review and analysis and a participatory staff workshop. The purpose was also to provide an opportunity to centre staff voices and strengthen team synergy and ensure consensus of how to ensure preparedness and ownership of future actions.

## Process and methods

The review was intended as a participatory, collaborative exercise, to enable staff reflection, engagement, and ownership of corrective actions. The process consisted of three key phases outlined below, with methods indicted for each:

- Initial data collection

- An online survey of EVD response staff including former surge staff (Annex B).

- Analysis of EMTs, 5Ws and SitReps.

- Creation of timeline with key dates.

- Workshops

- A participatory workshop in Kampala 21 March 2023

  - What went well/could be better (including prioritization)

  - Actions to improve (including prioritization)

- Supplemental data collection and synthesis

- key informant interviews (KIIs) of district task forces and front-line health and social workers in the field.

Further information on the methodology of the AAR is available in Annex C. In addition, detailed reports, and presentations from the group discussions for each response area are available in Annex D.

## Overview of the response

Over the last 25 years, Uganda has experienced several EVD outbreaks. Including the latest EVD outbreak 20 September 2022 the country has experienced seven EVD outbreaks (five Sudan ebolavirus, one Zaire ebolavirus and one Bundibugyo ebolavirus) since 2000. However, several parameters made the outbreak in 2022 different and more complex. The outbreak originated from Uganda, but the Ministry of Health has not been able to identify the origin. Although UCO has long experience of responding to disease outbreaks, it had not responded to an outbreak of this magnitude and had never responded to a L2 emergency.

Previous EVD outbreaks in Uganda

- 2022-2023: Sudan ebolavirus – 142 cases (55 deaths) in nine districts.

- 2018–2020: Zaire ebolavirus – 4 reported cases. All cases imported from DRC and all 4 cases passed away in DRC.

- 2012-2013: Sudan ebolavirus – 6 reported cases (3 deaths) in three districts.

- 2012: Sudan ebolavirus – 11 reported cases (4 deaths) in one district.

- 2011: Sudan ebolavirus – 1 reported case (1 death) in one district.

- 2007-2008: Bundibugyo ebolavirus – 131 cases (42 deaths) in one district.

- 2000-2001: Sudan ebolavirus – 425 cases (224 deaths) three districts.

The outbreak in 2018 reported four cases, all imported from neighboring DRC and all four cases passed away in DRC. Between 2012-2013 the country experienced two outbreaks - the outbreak in 2012 occurred in Kibaale District and reported 11 cases (four deaths), while the outbreak 2012-2013 reported six cases (three deaths). The outbreak in 2011 reported only one case (one death). In 2007-2008 the outbreak was bigger with 131 cases (42 deaths) and the outbreak in 2000-2001 was the biggest with 425 cases (224 deaths). As a result, the country office had not experienced a big EVD outbreak in 15 years.

In addition, no outbreak had spread to so many districts (nine) before, and it spread to urban areas (Kampala, Jinja). Due to these parameters the country office had to scale-up to a large-scale countrywide emergency operation. The spread of the outbreak required the country office to respond in multiple places at the same time. The country office scaled up from 25 staff normally working with emergency to 105 at the peak of the outbreak (including surge staff and TAs).

Furthermore, unique characteristics of the country required a highly adapted approach to programming. Uganda is a low-income country (US$884 per capita GDP in 2021) and one of the most populated countries in the world with a young population (over 45 per cent under 14 years old). Since the biggest Ebola outbreak in 2000 the Ugandan population has increased from 24 to over 48 million people, which affected the response and required close coordination and monitoring. The response involved political sensitivities to be navigated and the fact that 56 development partners were involved made the coordination challenging and it was initially difficult to have full overview and control of the response.

The timeline below shows how the country office responded immediately by supporting the Ministry of Health from day one and was operational in the field within less than three weeks, while maintaining a focus on staff safety bearing in mind the high risk of transmission of the virus.

Figure 1: Overall timeline of EVD response

UNICEF humanitarian programming in Uganda is guided by several key documents, mainly the UNICEF Uganda Humanitarian Action for Children (HAC) 2023, the Emergency preparedness and Response Plan, the UNCT Ebola Response Plan, and the National Ebola Response Plan. In January 2022 the UCO developed its Annual Management Plan (AMP) operationalize key priority areas needed to achieve the objectives laid out in these documents.

Initially, the EVD response was anchored around existing structures in the office, including COVID-19 task forces that were still in place. An EVD response plan, which was aligned with the Government’s response plan, including an appeal for US$ 18,257,400 (based on a worst-case scenario) was in place by 14 October 2022 (Annex E). On 27 October, the emergency was scaled up according to the corporate emergency activation procedure (CEAP) to a L2 emergency (see Annex F). With the activation of L2, UCO was able to draw on HQ and RO support and experience in delivering quick critical supplies to populations in need. However, the whole organization responded immediately, and UCO was supported through access to emergency preparedness funds (EPF loan) and surge deployment from RO and HQ before the activation of L2.

The response was relatively well funded, and UNICEF received US$8,218,223 from five donors (CERF, ECHO, Sweden, UK, USAID) to respond in the nine affected districts. The initial EPF loan and an innovative approach from HQ, which allowed UCO to reprogramme funding from other programmes for a temporary period played a crucial role for the immediate response.

The following chapters present the results of the AAR process and its examination of what went well and what could be improved in key aspects of the response. They will not present assessments of each programmatic area in detail but will highlight priorities to be addressed in the next phase. The planned evaluation will allow for more in-depth examinations.

# Key findings - What went well and what could be improved?

## Presence and positioning: are we in the right places at the right times?

| What went well - UCO’s existing structure in the field. - UCO’s strong leadership and coordination towards the Government and key stakeholders. - Rapid and timely deployment of staff resulting in timely on-ground presence. | What could be improved - Clarity/improved internal coordination on roles and responsibilities within the office and towards the field to ensure a more uniform and comprehensive response in the field. - The role of the RC. - Weak coordination structures at government sub-national level need to be strengthened. |
| --- | --- |

UNICEF Uganda operates in 29 districts of which four districts were affected by the EVD outbreak, while the other five EVD affected districts were geographically very close to where UCO operates. UCO’s already strong presence and network in the field made it possible to respond immediately.

Figure 2: UNICEF focus districts and EVD outbreak districts

Overall, staff members showed a high level of flexibility and willingness to support the response and a key strength of the response was UCO’s ability to rapidly deploy staff in the field. The decision to establish EVD Hubs in affected regions (Mubende, Kampala, Jinja and Makara Districts) was vital and made it possible for UCO to have staff, supplies and infrastructure permanently available in the field and it ensured timely on-ground presence over a longer period. The Hubs coordinated the response effectively and reports were shared daily.

UCO’s strategic positioning and continuous engagement at all levels of the response (national task force and district task force) was important in ensuring key issues relating to children were incorporated into the overall response. For example, the inclusion of child protection and MHPSS on national level. UCO had a good collaboration with the Ministry of Health (MoH) and development partners. The UCO supported coordination of the response at both the national and sub-national level by playing an important role in the Government pillar structure and by deploying field coordinators to the five hubs, under the leadership of the Ebola coordinator. The coordinators actively engaged with and supported the government’s leadership and partners and were involved in the planning and monitoring of the response and provided regular feedback.

In addition, UNICEF led and supported a multi-actor, agency, and disciplinary integrated outbreak analytics (IOA) cell that guided the response using transdisciplinary data. This was based on best practice developed, evaluated, and modelled during recent outbreaks of EVD and other diseases.

Although UCO responded rapidly there is room to improve the internal coordination and clarify management roles. For example, the survey showed that several staff members raised concerns of not knowing who was leading the response. The EMT and TET was chaired by the Representative, which was highly appreciated, but several other colleagues were given leadership roles and it was often difficult to know who was in charge daily. As a result, several UCO staff members, in particular in the field, felt frustrated and it was unclear what should be done by whom and when. For example, staff deployed to the hubs in the field faced unclear instructions and reporting lines and insufficient communication internally, which resulted in a less efficient execution of the response. For example, the supply team ended up undertaking reverse logistics.

Recommendation:

- UCO to ensure clarity on the roles and responsibilities of surge positions on deployment (including coordination) visa vis the existing country office structures.

- UCO to update and implement HR/Surge plans and streamline reporting lines and deployment modalities.

- UCO in collaboration with RO to enhance the WHO/UNICEF coordination as well as advocate for whole UN approach to similar responses and reference the UNICEF-WHO MoU on health emergency preparedness and response (see Annex F).

- Strengthen inter-agency coordination mechanism clearly discerning roles and responsibilities and advocating for an improved leadership role of the RC during public health emergencies (PHE) in collaboration with other UN agencies/emergency response actors.

At the initial stage of the outbreak, the Government formally asked WHO to coordinate the response. As a result, the RC did not get a clear leadership/coordination role, which resulted in unclear roles and responsibilities among the different UN agencies. Furthermore, the inter-ministerial coordination was not always as efficient as needed. For example, relevant ministries were not always included in the pillar working groups, which slowed down the response. The Government pillar meetings were often very lengthy, and UNICEF had to spend time in meeting rooms instead of being operational in the field. The government took on the leadership immediately, but the sub-national level was not given a clear role and thus not on its responsibility. In addition, the high number of 56 partners to the Government caused a challenge and as a result, the Ministry of Health created accountability forums to solve issues such as unclarity of funding, public mistrust, and to ensure the overall control of the response.

## Preparedness and planning

| What went well - Structures in place that facilitated immediate support to government partners. - EMT structure in place, re-activation of COVID-19 structures in the field and RCCE EVD response plans speed up the response. - High percentage of staff had experience from previous EVD outbreaks. | What could be improved - Initial delays in design of response and rollout of critical interventions due to lack of public health emergency plans for most sections. - Initial implementation was done in silos due to limited horizontal integration. - Strengthen the role of the field offices. |
| --- | --- |

UCO has long experience of working together with and supporting the Government and its partners, both on national and sub-national level through formal and informal structures. UCO’s broad and extensive network made it possible to immediately start supporting the Government. Already the same day as the outbreak was declared UCO attended meetings on national and sub-national level.

The EMT structure was already in place, and it was immediately expanded to include colleagues from all sections and not only emergency colleagues. SBC section had the 2018/19 MoH Risk Communication Implementation plan, which was quickly updated and made it possible to respond immediately and send important risk communication messages in the right place at the right time. In addition, although the national health system was still recovering from COVID-19, UCO could benefit from internal COVID-19 structures that were re-activated and speed up the response. The L2 Benchmark indicators and dashboard were updated daily. In addition, all information shared by the Ministry of Health was summarized in a user-friendly format (see Figure 3 and Annex E).

Uganda is not a humanitarian response plan (HRP) country, and therefore, does not have the cluster-based emergency planning system. As such the UCO emergency preparedness planning process was guided by the 2023 Humanitarian Action for Children (HAC), which was based on a multi-hazard preparedness plan. The preparedness planning was triggered by a risk analysis, which was based on the evolving country context.

By the time of the EVD outbreak, UCO had a multi-hazard emergency preparedness plan which anticipated, among others public health emergencies (including EVD outbreak). The plan identified the anticipated people in need as well as the anticipated people to be reached in the event of an outbreak. These planning figures were uploaded onto the emergency preparedness platform (EPP). The figures were used to update the office minimum preparedness standards, including the standing capacity, staffing needs, and supply needs.

At the time of the risk analysis (around July 2022), EVD had not been flagged as “very high risk” thus there was no EVD-specific contingency plan. At the initial phase of the outbreak SBC section, as mentioned above, could update an old plan but none of the other sections had prepared an EVD response strategy. This was a challenge in the beginning of the response, and the importance of having public health emergency plans in place was discussed at length during the workshop. Furthermore, due to the absence of response plans, the initial implementation was done in silos and with limited horizontal integration and the UCO did not deliver as “one office”. During the workshop, most participants agreed that this was a key weakness, and the office should invest time in looking into the issue to ensure an “one office” approach for future emergency response.

However, as soon as the EVD outbreak was declared, an UCO EVD Response Plan was developed and rolled out aligned with the Government EVD Response Plan. The UCO EVD Response Plan activated the existing UCO emergency preparedness plan, which was uploaded on the EPP.

The absence of response plans in the initial phases was partially compensated by the fact that several staff members had experience from previous EVD outbreaks.  Around 50 per cent of the respondents in the survey responded that they had participated in previous EVD responses. Out of these, almost 70 per cent thought previous experience and lessons learned from previous outbreaks were taken into consideration during the response 2022. This was a clear strength during the response and UCO could benefit from knowledge and advice from EVD experienced colleagues. For example, the Ring IPC approach was successfully used with good results.

A clear majority (69.56 per cent) of the respondents in the survey thought UCO was programmatically prepared for the outbreak and almost 74 per cent thought UCO was fit for purpose.  However, there is a recommendation to strengthen the operational and logistical preparedness for a more decentralized response by reinforcing the role of the field offices and the capacity of staff in all sections in emergency preparedness and response.  Moreover, this was the first time UCO responded to a L2 emergency and there was not an office-wide understanding of the L2 emergency procedure, which resulted in delays in parts of the response. For example, knowledge about the simplified procedures for partnerships. It would be good if RO, as responsible for L2 emergencies, could support country offices with an orientation on L2 procedures.

Recommendations:

- Strengthen capacity of staff in all sections in emergency preparedness and response and L2 procedures. As part of this, RO to consider an UCO office wide orientation of the L2 emergency procedures to ensure a common understanding for both programme and operations.

- Benchmark international guidance and design a clear minimum of emergency intervention packages for each response area to improve horizontal integration in interlinkages during emergency response and delivering as “one office”.

- Harmonization of the Emergency Preparedness and Response Plan, including prioritizing the development of a comprehensive PHE strategy/plan taking into consideration the recurrent disease outbreaks experienced in Uganda.  RO to share a template on PHE planning.

- Consider conducting simulation exercises to test, validate and enhance preparedness and response plans, procedures and systems for all hazards and capabilities, including for PHEs.

- Look into how existing COVID-19 structures can be used also in the future. For example, using the trained and empowered school health teams (headteacher, teachers and students) and village health teams.

- Develop a health service continuity plan to ensure continued delivery of essential health services in the case of a public health emergency or anticipated shocks to health systems. Lessons learnt during COVID-19 response, including alternate delivery mechanisms to be incorporated in the plan.

- Strengthen the role of UCO field offices during emergency response.

In 2020, RO and HQ supported a planning, cross-border coordination, and preparedness exercise in six EVD outbreak experienced countries (Uganda, South Sudan, Kenya, Tanzania, Burundi, and Rwanda). Lessons learnt from previous EVD responses based on the exercise were shared with UCO in a report at the onset of the response (see Annex G). The lessons learned were integral in guiding planning efforts to implement best practices and mitigate anticipated challenges.

## Programmes: Are we child-centred and meeting the greatest needs?

| What went well - Early decision to have a child focused response due to higher representation of cases among children guided the overall response throughout the emergency. - Programme effectiveness with high achievements of outputs. | What could be improved - Lack of ORE funding for needed BEAD interventions; initial lack of allocation of funds for CP/MHPSS. - Integration of protection in the response was a challenge due to the absence of dedicated coordination fora for protection. Child-centredness could be strengthened across UNICEF sectors. |
| --- | --- |

During the outbreak, children were more vulnerable to the disease and had an overall higher fatality rate (43 per cent) than adults (39 per cent) and it was even higher in the beginning of the outbreak. The fact that children were more exposed emphasized the importance of approaching the outbreak differently. In addition, among 56 partners to the Ministry of Health, UNICEF had a clear child rights role to play. For example, UNICEF helped developing guidelines on how to specifically support children and protect them, guidelines for continuity of learning and health service delivery, RCCE messages were developed for children, a child friendly environment was guaranteed in the health facilities including child friendly nurses, toys, lowered washing stations and children were put in rooms with windows so they could communicate with their families. Decongestion through high performance tents enabled treatment of the top child killers like pneumonia, diarrhoea and Malaria. Breastfeeding women were supported with RUIF. All interventions can be found in Annex H.

An EVD response plan was developed with benchmarks, outputs, and indicators. While this review does not provide an in-depth assessment of results in each area, a summary of programme results is shown below:

Figure 3: L2 benchmark indicators – Uganda EVD response

The table shows that UCO effectively met the greatest needs during the response with 10 out of 12 L2 benchmark indicators indicating a high result. Existing structures, network, flexible staff, previous experience, and support from other UNICEF offices supported this result.

The resource mobilization output indicates low result. However, the response plan included a worst-case scenario with 22 districts affected. Thus, the resource mobilization target was set to support all districts in the country. The worst-case scenario never occurred and the received funds for the nine affected districts were sufficient although the benchmark table shows the opposite.

Recommendations:

- UCO should advocate for the integration of Child protection and MHPSS in all future public health emergencies.

- UCO should advocate for the integration of Education in all future public health emergencies.

- UCO should also advocate for child disaggregated data in future emergency response.

Initially, the Government had a strict health perspective of the outbreak and child protection including psychosocial support, protection issues and the well-being of children were not integrated in the response. As a result, there were no dedicated coordination for child protection issues. UCO efficiently advocated for the inclusion of MHPSS in the response and it was included three weeks into the response. Consequently, programme activities and funding for Child Protection came in late. Furthermore, initially Education section was not part of the response and interventions in schools were covered by WASH as part of UCO’s infection prevention and control support. President Museveni’s decision to impose movement restrictions in Mubende and Kassanda Districts changed the needs for Education section to be part of the response by supporting students to write their final exams and to move in and out from the restricted districts. Even so, Education was never included in the government response plan and as such made it difficult to raise funds for important education interventions. The issue was solved thanks to flexible thematic funding.

## Partnerships: Are we strategically engaging with the right partners?

| What went well - Partnerships with relevant partners were already established. - Capacity building of groups/partners from the whole society (incl. religious, political and community leaders, journalists, traditional healers, boda boda association, private sector and other relevant groups enabled a quick response on all levels in society. | What could be improved - PCAs with relevant partners should be prepared ahead of an emergency. - Recognition of health workers needs to be improved to encourage ongoing health services during outbreaks. - Government had inadequate staffing for implementation of the response. - Ensure UNICEF knowledge about EVD response is documented and shared. |
| --- | --- |

Partnerships with both government, sub-national level and CSOs were rated as a strength during the response both in the survey and during the workshop. Partnerships with other UN agencies were also mentioned as a strength in the anonymous survey but it was emphasized during the workshop that partnerships with other UN agencies had been challenging and needs to be strengthened.

Figure 4: UCO staff survey: Partnerships

UCO had well established partnerships and before the EVD outbreak, UCO was working with 100 implementing partners (17 CSOs and 83 government partners, representing US$17,915,978 million at the time of declaration of the outbreak), covering all programmatic sectors. This was a strength during the response. For example, SBC section had PCAs with relevant partners (such as URCS and LWF), which played a key role in the response and made it possible to scale up rapidly. This enabled the engagement of local leaders in the mobilization process, reaching the hard-to-reach communities, which led to faster response to the concerns of the affected communities, improved trust, and more efficient delivery of key inputs such as IEC materials, jackets, and payment of allowances to community-based mobilisers and village health teams. Public awareness was raised through social media channels such as WhatsApp but also by toll-free hub lines, direct communication with megaphones and community towers. Capacity building interventions were organized with influencers such as religious, political and community leaders and traditional leaders but also other groups in society such as the boda boda association. However, most sections did not have PCAs in place for the response and this was a key lesson learned during the workshop.

The Private Sector Engagement unit provided private sector partners with soft copies of risk communication and IEC materials which were distributed to estimated 6,450 businesses in Uganda. Key partners including Standard Chartered Bank printed and distributed these materials across location throughout the country.

The CAP section also brought together Kampala-based editors and journalists nationwide for orientation training on accurate, responsible, and ethical correct reporting to curb fake news and misinformation. Due to lack of existing media training materials on EVD in English (across the world), UCO CAP contacted WHO AFRO and was deferred to WHO and UNICEF in DRC to learn from their experiences. Media training documents were translated from French to English and made Uganda context specific. The country-wide media training intervention was successfully implemented and reached some 358 media professionals. As a result, fake news was avoided, mis and disinformation reduced, and journalists and editors knew where to seek information about EVD. The close collaboration with MoH and WHO was effective and harmonious.  WHO produced joint visibility materials for the EVD outbreak, and the Minister of Health had her first ever platform to interact with editors of Kampala based media. It is recommended to ensure best practise is documented at a central point for future public health outbreaks.

A considerable number of staff viewed implementing partner procedures overall as heavy, with perceived long timelines for HPD review and signature. This was despite the decision to not use the more time-consuming standard partnership review committee (PRC) process.

UCO worked closely with the health sector on all levels and provided capacity building on EVD and how to reduce the risk of transmission. For example, special attention was given to the village health workers, which was an exposed group. Although, UCO and other EVD partners to the Ministry of Health supported the health sector, many health workers were over stretched. The situation was discussed during the workshop, and it was agreed that UCO needs to advocate for recognition of health workers and look into how it is possible to encourage them to ensure a continuation of health services during future public health outbreaks. Such advocacy is intended to maintain and/or improve the morale of the limited staff members at government health facilities. For example, it can be addressed by working with MoH to nominate and award certificates or in-kind rewards to outstanding health workers. This is closely linked to the inadequate government staffing situation throughout the response.

Recommendations:

- Adopt emergency friendly solicitation and deployment of partnerships.

- Advocate for the recognition of health workers and how to encourage them during a public health outbreak.

- Ensure all success stories from the EVD response are documented and shared with relevant staff in HQ for future public health response.

## Operations: Are we delivering in the most timely and efficient way?

| What went well - Immediate access to internal funding that allowed flexible implementation. - Availability of LTAs for transport, accommodation, safety kits and fuel. - Innovative methods of paying partners enable a more efficient implementation. | What could be improved - Need to include Operations and HR from day one. - Ensure preposition of equipment to ensure staff safety and well-being during public health emergency. |
| --- | --- |

A key strength of the overall response was swift access by UNICEF of its own flexible funding at the initial phase of the response. Firstly, UNICEF HQ showcased its ability to respond quickly by immediately approving an EPF loan. Secondly, it was possible to re-programme existing COVID-19 funds to EVD response and lastly, flexible donors allowed reprogramming of thematic funding. All these factors enabled immediate and flexible implementation. The overall funding appeal US$18,257,400 was based on a worst-case scenario, that fortunately never occurred. UCO received a total of US$8,218,223, which was efficient to support the nine affected districts. Funding was received from UNOCHA (CERF), ECHO, Sweden, UK, and USA and mainly negotiated locally.

Supply delivery cuts across all programming areas and, like partnerships, lies at the intersection of programmes and operations. Initially, remaining COVID-19 PPEs and other supplies enabled a quick response. For example, high performance tents, which were meant for Education section were immediately dispatched to set up isolation centres for EVD. Prior to the COVID-19 pandemic UCO had an LTA for gloves, which supported the response. In addition, items like sanitizer, handwash facilities and printing services were already on LTAs. The activation of the L2 helped the Supply unit to procure and approval in the shortest time possible. The warehouse throughput for EVD response was over US$885,000 and included items like gumboots, heavy duty gloves, hand Sanitizers, mobile plastic toilets, pull up banners, posters, EVD fact sheets, thermometers, washing machines, job aid cards, high performance tents, calcium hypochlorite, sprayers, aprons, and liquid soap. In addition, the Supply unit issued contracts for drilling of boreholes and installation of water supply systems in three health centres and there was also some electrical rehabilitation works at a health centre and an incinerator.

The administrative section had existing LTAs with enough companies and the response never experienced any bottlenecks due to issues related to lack of transportation, fuel, accommodation, and safety, except in Mubende district where many implementing partners needed accommodation at the same time and it was important to ensure safety.

However, as for most other sections Operations section did not have a response plan, and this resulted in ad hoc solutions. It is recommended that Operations section is integrated in all section’s response plans but there should be a separate response plan for Operations.

Recommendations:

- Establish a plan how RO can support UCO and explore funding options during the onset of future emergencies, such as pandemic funds and First Action Initiative.

- UCO to develop a resource mobilisation plan/concept notes for emergency response.

- Operations to be included in all section’s response plans but also have its own plan, which should include staff safety.

- Document good lessons learned from using innovative ways of using mobile money.

UCO included innovations in the response and one success was the use of mobile money to pay partners to speed up the response. The usual way of paying partners through DCTs would take long and UCO established a system where large number of transactions processed directly to beneficiaries through bulk mobile transfers. Moreover, cash withdrawal functionality of Pcards were activated that enabled the coordinators to withdraw cash from any ATM machine. This allowed UCO to timely respond to low value, time sensitive and critical activities.

## People: Are we adequately leveraging our most valuable resource, UNICEF personnel?

| What went well - Rapid staff scale-up thanks to flexibility among UCO staff members and surge staff. - Leveraging on already existing IPs and other partners on ground. | What could be improved - The pace of the disease out weighted staffing capacity. - Duty of care was more focused on field staff and not Kampala staff. |
| --- | --- |

The EVD outbreak moved fast, with a big uncertain how it would develop. In this situation, the organization responded immediately, and UCO staff showed high flexibility and willingness to support the response in any area and in any part of the country and often worked in stressful and uncertain conditions. This commitment was a key strength of the response and showcase the strong culture of accountability towards the Core Commitments for Children. In addition, RO started supporting UCO from day one and UNICEF colleagues with EVD experience and other relevant experience joined the office.

During the response, 56 UCO staff were redeployed, 12 surge staff and 37 TAs were recruited to support the response. In total, 105 staff worked with the EVD response. Most of changes of staff and recruitment of surge and TAs happened during the first and second week of October. The rapid scale up was supported by a recruitment push with an average speed of 10 days for EVD recruitments.

Figure 5: Number of staff during EVD response, September 2022 – March 2023

| UCO staffing capacity during the L2 |  |  |  |  |
| --- | --- | --- | --- | --- |
| # UNICEF Staff Redeployed | # Surge Staff | # SBP | #TAs | Total |
| 56 | 12 | 0 | 37 | 105 |

During the workshop several UCO staff expressed satisfaction of being part of the response but also raised concerns over the pace of the disease resulting in exhausted staff. The UCO had a well-establish duty of care for the field, but several staff emphasized the need to include Kampala office.

## Response effectiveness for programme sections

Chapter 7 will reflect on the programme sections while Response area 1 (coordination, leadership, and partnerships) and Response area 7 (logistics and operational support) have been described in previous chapters. Response area 3 (surveillance and contact tracing community) was covered under Response area 5 (case management) during the workshop. Detailed reports for each response area can be found in Annex C. The recommendations for each programme section include how big impact each recommendation would have (*** very high, ** medium and *low impact).

Response area 2: Risk communication, social mobilization, community engagement

- Preparedness: SBC section was well prepared for the outbreak and had an institutional memory from past EVD outbreak responses and had the 2018/19 MoH risk communication implementation plan, which was updated. Previous COVID-19 guidelines and plan added value to the EVD preparedness. The SBC section is co-lead to the RCSM sub-committee (led by Ministry of Health) and the 4W matrix was in place and used to coordinate and guide planning and implementation of activities. Previous EVD templates and budgets were used to generate DCTs and plans on district level.

- What went well/best practice: SBC had access to funding immediately and could rapidly deploy people. They had an important coordination role on national level as sub-lead to the RCCE and community engagement pillars. A monitoring framework was developed at the beginning of the outbreak and made it possible to keep track of data and daily reports were shared. SBC, through existing networks and partnerships delivered timely messages to the public and reached 5.9 million people. Training of journalists and timely community feedback made it possible to avoid spread of rumours and myths. Capacity training was provided to key influencers such as political, community leaders, religious, traditional healers, and associations such as the boda, boda association. Good visibility was ensured by photo documentation, news stories and human-interest stories.

- Recommendations (in order of impact):

- RCCE preparedness using the DDMCs structure under OPM. (***)

- Advocacy for reuniting the RC and CE pillars. (***)

- UN RCCE coordination mechanism required. (**)

- Integrated and costed community engagement package. (**)

- Inclusion of HR, admin, and finance in onboarding/orientation of SBC RCCE staff (cuts across all sections). (**)

- Strengthen RCCE district emergency operations systems and structures.

- Consider early engagement of key influencers at the onset of the outbreak or any emergency response.

- Use of children as change agents and RCCE activities.

- The MoH 2023 National After Action Review (AAR) for the Sudan Ebola Virus Disease (SDV) outbreak in Uganda recommends the establishment of systems for social listening, community feedback, and evidence generation at all levels, especially at the district and sub-district levels, and to take advantage of the existing broad media network to increase community education programs on public health emergencies across the country.

What can we do better/challenges: SBC experienced delays in the deployment of the ten recruited SBC surge staff and peer reviews for PDs and implementation of RCCE activities. Some partners were overstretched. For example, Uganda Red Cross Society was overloaded and accepted funds from many different partners. It was difficult to implement RCCE activities in Mubende and Kassanda Districts during the movement restriction period. It is also important to look into how to communicate sensitive matters such as communication with EVD affected families. RCCE funding was not fully utilized during the response due to bureaucracies between the districts and the Ministry of Finance. The collaboration between pillars should be strengthened. There was an unnecessary “competition” between UNICEF and WHO with both organizations fundraising for RCCE and WHO also deployed RCCE staff. The ToRs and the coordination of the surge consultants recruited through SBC and CSD sections, to support Risk Communication and Community Engagement, respectively, should be refined to avoid duplication of efforts and operation in silos.

Response area 4: Water, Sanitation, and Hygiene Promotion (WASH)

- Preparedness: The WASH section was engaged at the national and sub-national level including districts, and deployed staff at an early stage. The response mechanism of WASH/IPC at the sub-national level (led by ADHO Environmental Health) was in place and was easily incorporated in the response structure. Also, the readiness assessment toolkit (scorecard) was readily available.  At the national level, UNICEF WASH was a lead participant in the WASH sub-pillar coordination mechanism under MoH, led by the Environmental Health Department, feeding into the National Task Force.

- What went well/best practice: WASH/IPC benefitted from strong coordination structures with partners at district level. WASH supplies were delivered timely responding to critical requests and needs. Also, efficient contractual procedures for the service providers were used. End-user monitoring and post-response monitoring of WASH/IPC items was executed as planned. WASH/IPC training was provided through various approaches including on-site mentorship of frontline health workers and by targeting multi-sectoral stakeholders (district health officers, health workers, and community members). This led to efficient and effective resource utilization and reduced the burden of community mobilization. Additionally, this strengthened integrated community-based WASH/IPC activities on the ground. Last mile transportation was also utilized by WASH to ensure timely delivery of critical WASH/IPC supplies reaching target beneficiaries including health facilities and schools.

- Recommendations (in order of impact):

- Review coordination structure for WASH/IPC pillar(s) - National vs districts (***)

- Clear roles and responsibilities within the national pillar. (***)

- Ensure L2 procedures applied to expedite procurement - Preparedness of LTAs and HPDs (stand-by partners) in place. (**)

- Periodic simulation/planning exercise to ensure contingency plans/toolkits in place – including when/how to conduct inter-action reviews, monitoring requirements, HR deployment, staff re-assignment mechanism. (**)

- WASH/IPC supply/logistics - Last mile distribution budgeting and standardized in PHE response and Predefined supply plan for visibility/branding (*)

What can we do better/challenges: The coordination mechanism at national level was unclear and there was a duplication of readiness assessments (IPC scorecard versus Ministry of Health WASH rapid assessment for health facilities). Supported schools were not assessed. There was limited pre-deployment orientation of staff (for example for Masaka District). Sanitary supplies should be included in the standard WASH/IPC package for health facilities and schools. The functionality of handwashing facilities needs to be prioritized as well as ensuring the capacity to manage and maintain them. There were gaps in training of health facility staff (Hygiene and IPC/WASH practice)

Response area 5: Case Management

- Preparedness:

Child Protection: The National Child Policy existed but had not been disseminated in KCCA area (Kampala). There was an emergency response plan on national level but not for Kampala. Ministry of Gender, Labour, and Social Development (MGLSD) struggled to fit into the National EVD response plan and many of the pillars and activities had little to no social welfare accommodation. Coordination and leadership by MGLSD were lacking and the ministry was not really involved and did not take up any role in the EVD response. The Ministry had not played any role prior to the outbreak in coordination of CP/MHPSS interventions in health emergencies. MHPSS sub-pillar coordination at national level existed although not very active and there was no sub-pillar coordination in the field prior to the outbreak. Sub-national coordination differed a lot in quality and capacity.  It was unclear which pillar child protection belonged to and it fell under MHPSS although child protection is bigger.

Protection from Sexual Exploitation and Abuse: The following PSEA policies and systems were in place before the outbreak: victims assistance protocol, SOPs on receiving, recording and referring SEA cases, ToR for PSEA focal points at section and zonal office and the interagency ToR for PSEA focal points was in place. The south-west PSEA agency technical working group was active in Mbarara chaired by UNHCR and co-chaired by UNICEF and PSEA Inter – agency technical working group was active to steer PSEA efforts in the response. At the National level, the interagency PSEA technical working group was active, and met monthly. At the sub-national level, the south-west interagency PSEA network was active, and was meeting bi- monthly.

Nutrition: The following policies were in place: SOPs on Nutrition and Child Feeding in the context of Ebola Viral Disease (EVD); Integrated Management of Acute Malnutrition (IMAM) and Maternal, Infant and Adolescent Nutrition (MIYCAN) guidelines; Monitoring and Evaluation tools for Nutrition in Emergencies; Nutrition Section had emergency response plans in place from previous emergencies; SOPs were updated to incorporate learning from other ebola affected countries; Internal guidance on Nutrition and IYCF in EVD provided by UNICEF RO and; Ready to Use Infant Formula (RUIF) requisition guidance and templates in place. A Nutrition technical working group existed at National level, but it was dormant, and no discussion happened on EVD, including on any other such emergencies. There was no adequate capacity on Nutrition in affected Districts and staff were not mentally and technically ready to face the EVD outbreak.

- What went well/best practice:

Child Protection: Child protection and MHPSS was fully integrated within UNICEF’s response and the government response plan after successful advocacy from UNICEF. Joint training with WHO on PSEA at field level was conducted in a very timely manner. Collaboration with ECD team resulted in individual play kits.  Successful identification of an EVD survivor – in collaboration with WHO and MSF and development of a SOP on engaging survivors. Child protection used active CSO partnerships to strengthen systems to respond to the remaining needs whilst strengthening. Child friendly emergency treatment unit (ETU) guidance was developed and inter-agency PSEA network was quickly activated. Quick identification of the CHL as the key reporting mechanism for SEA and training of counsellors will also result in longer-term benefits. Leveraging of para-social workers and capacity building on MHPSS through health workers, with capacities remaining behind beyond the response. In addition, integrating MHPSS aspects of EVD into clinical case management protocols to mitigate the impact of stressors associated with the disease i.e., quick development of child-friendly ETU guidance, play kits and SOPs on engaging with survivors, integrating MHPSS messages in RCCE work and leveraging existing partnerships to respond, and building MHPSS capacity among para-social workers and health workers. While lack of a pre-existing MHPSS structure was a limiting factor at the outset of the outbreak, consequent engagement with MHPSS partners in EVD clinical care resulted in changes in ETU organizational structure making them friendly and safe for patients and their families, thereby improving the overall clinical care and promoting community trust and engagement.

Protection from Sexual Exploitation and Abuse: Inclusion of PSEA/GBV as key components of the EVD response was crucial. PSEA/GBV orientation and training of frontline workers, including District Local Government Officials in the affected districts from the onset of the emergency was also key in streamlining PSEA/GBV in the response.  Engaging the affected communities in designing community-based complaint mechanisms (CBCMs)ensured ownership of the response by the locals because their voices were considered in the design of these CBCMs.

Child protection and MHPSS:

The response work was strengthened thanks to CP/MHPSS teams in CO, ZO and newly deployed staff worked well together. Integration of MHPSS messages in RCCE work in Masaka District worked well. The collaboration between health and social welfare at DLG level increased and was excellent. Quick activation of partnership with Butabika and strong collaboration in a real partnership approach was successful.

Nutrition: Timely updating of SOPs and guidelines on nutrition response in EVD contexts and prioritization of nutrition indicators for EVD. Overall support from RO was very helpful and cross-country learning with DRC and RO was very fruitful. The ordering of RUIF and prepositioning to ETUs was done in a timely manner. Integrating RCCE, CP and WASH into nutrition capacity building at national and sub-national levels was successful. redeployment of staff from other programme areas to support nutrition.

- What can we do better/challenges:

Overall challenges: Engagement and service provision in non-UNICEF focus districts was a challenge at the start of the response. Delays in internal procedures to approve PDs. For example, some PDs started two weeks before EVD was declared over. Siloed nature of the emergency

Child protection: It was unclear where CP fell in the government pillar structure and DLGs had too little pre-existing understanding on their role in CP in health emergencies. MGLSD did not get involved in the response at all. There were no pre-existing play kits for individual play available for the response. Standby partnership was in place, but there were no partners with specific expertise in Child protection in EVD response. Partnership development should have followed L2 procedures – procedures remained too heavy and slow. Stronger involvement by the whole CP team in areas of responsibility was needed. Quick reactivation and engagement of community-based child protection networks including para-social workers, child friendly space facilitators, child protection committee (CPC), village health teams, LC systems to provide prevention and response interventions to survivors, patients, suspects, and their families in affected EVD localities is very important in provision of immediate response interventions.

Protection from Sexual Exploitation and Abuse: There was funding gap at the very onset of the emergency and this in a way affected PSEA immediate interventions especially when it came too providing survivor/victims’ assistance. The EPF funding came towards end of November, yet the EVD outbreak was declared in September.

CP/MHPSS: Sub-national MHPSS sub-pillars had to first be established, and there was limited understanding at DLG level on the importance. There was no pre-existing UNICEF strategy on how MHPSS would be practically integrated in a response prior to the outbreak. Except Masaka District, integration of MHPSS and CP messages in RCCE work never happened. Internal advocacy and convincing was required before financial resources were allocated for MHPSS and Child protection. Deployment of international MHPSS Specialist standby partner function didn’t work. HQ support came in at the tail end of the response.

- Recommendations (in terms of impact):

Child protection:

- General capacity building on child protection in emergencies, including health emergencies for all UNICEF staff to boost response capacity.

- UNICEF to work with MGLSD to ensure that in future health emergencies they take a leading role.

- COs need to fully adopt the L2 procedures, including for partnership development (i.e., no ICE, startup letter, blanked support costs, etc.).

- In future, a pillar on continuity of (all social) essential services, not just health, and advocate with government on this

Protection from Sexual Exploitation and Abuse

- Continued capacity strengthening of para-social workers on their role in MHPSS in (health) emergencies.

- Engagement internally to bring more clarity on where MH sits within UNICEF.

- Be proactive and develop integrated SBC messages inclusive of MHPSS and CP.

Nutrition

- Capacity building on IYCF and RUIF before prepositioning is required.

- Preparedness activities are needed in districts very prone to emergencies even if they are no focus districts.

- Continued capacity building on CCCs related to nutrition for UNICEF staff across CO and ZOs, with focus on staff with less emergency experience.

Nutrition: Ministry of Health staff were not knowledgeable on nutrition in EVD contexts, and the continuity of care was weak. It took too long to systemize an effective coordination. RUTF was delivered in the ETU, and there was an assumption that health workers would understand, which wasn’t the case. Integration of nutrition messages in messaging was not timely and that was a missed opportunity. SOPs on nutrition in EVD response was approved but too late.

Response area 6: Prevent and address the indirect impact of the outbreak

- Preparedness:

Support the safe continuity of essential health services to women, children, and vulnerable communities: Guidelines were available and plans for the polio and Malaria and child health diseases were already in place, which were adjusted in view of EVD. Re-activation of COVID-19 structures like village health teams supported the response.

# Support to households directly affected by EVD including survivors and chronically poor households to meet their basic needs: Social protection was included in the HAC 2023 but was not included in the multi-hazard response plan.

Continuity of Learning:  There were no preparedness and reponse plans specific for EVD, but the multi-hazard HAC was avaialble. Other specific plans such as COVID-19 and safe re-opening of schools were available but had to be reviewed to include EVD response. HOPE districts like Kyegegwa had a multi-hazard Contingency Plan developed with the training and support of Ugandan Red Cross Society. The experience from Kyegengwa was used to develop an EVD response plan. 2018 Ebola plan was in place but had to be updated to suite the 2022 EVD.  Coordination structures like the School Health Team at national level was active, the COVID-19 task force at sub-national and school level were available but inactive.

- What went well/best practice:

Support the safe continuity of essential health services to women, children, and vulnerable communities:

The national level coordination mechinism for CEHS with UNICEF as a co-chair worked very well. Revised and dissminated guidelines for CEHS amidst EVD folloing the previous COVID-19 guidelines with clear link to IPC.

Health facilities readiness in the EVD districts and other prepredness districts including Mukono, in view of CEHS with 20 KPIs  was conducted. MDA for Malaria as a common mordidity among children in Mubende and Kassanda Districts for children 3 months to 15 years was also supported. The provision of tents to support decongestion of patients in health facilities and screening/triage. The provision of logistics support, including fuel to ensure the district health teams could monitor the service utilisation and response. Food support to isolation sites. The continuation of nOPV2 campaign exercise in the rest of the country except five districts (Mubende, Kassanda, Kampala, Wakiso and Mukono). Through SBCC communities were engaged on the importance of continuity of essential health services. In collaboration with Child protection section, additional HR was supported in ETUs to ensure a child friendly environment for children. Capacity building was done support the village health teams to conduct the house-to-house monitoring and sensitisation of communities.

# Support to households directly affected by EVD including survivors and chronically poor households to meet their basic needs: UCO ability to roll out the socio-economic impact assessment of EVD contributed to the overall understanding of the impact on household welfare during EVD. The assessment will be used for learning purposes for future public health outbreaks.

# Continuity of Learning: The Incident Commander for school-based surveillance was recruited by UNICEF and deployed in Ministry of Health. Strategic collaboration and networking with key stakeholders at Ministry of Education and Sports e.g the director of education who happened to be the team leader of the Ministry of Education and Sports played an important role. The flexibility with cash transfers and re-programming of existing funds enabled education interventions. Smooth real-time data was collected by using Kobo collect app. Strong internal collaboration with other supporting sections e.g, Operations provided adequate and timely transportation and SBC supported with the infra-red thermometers.

- What can we do better/challenges:

Support the safe continuity of essential health services to women, children, and vulnerable communities:

# Continuity of essential health service as a pillar was not well empahised at sub-national level during the EVD response and UNICEF had to step in to ensure coninuity of services. Patients in isolation were not recieveing appropraite treatment for other diseases such as HIV, chronic diseases and  Malaria. The second MDA was stopped due to limited resources. Outreach activities in some areas were stopped or conducted irregularly due to the fear of EVD. The Western Uganda health worker’s knowledge of nutrition services was limited. Implementation was delayed due to resources arriving late at district level.

# Support to households directly affected by EVD including survivors and chronically poor households to meet their basic needs: It is critical that a clearly definied minimum package of response for UCO is defined and social protection should be included in all aspects, including fundraising and programme delivery. During the resopnse, there was no direct support through social protection to support the households, which became a missing link. The exclusion of social protection, specifically cash transfers, created a gap in the overall effectiveness of the response as households in the affected districts were exposed to deficits in food and non-food supplies, especially upon recovery.

Continuity of Learning: There was a lack of a contingency plan for Education to guide the response and absence of readily available accurate data for decision making. Another challenge was the lack of an Education specific coordination mechanism to guide the response at the field level. The pace of the disease outweighed staffing capacity and it was difficult to engage with district level stakeholders especially in non-focus districts and there was no pre-positioned of supplies and materials. In a few cases, staff supporting the response had language barrier especially when it came to community engagements. A bigger issue for UCO in the ambition to operate as one office was the fact that different modalities of facilitation was used across UNICEF. For example, in Kyegegwa health staff were given UGX 5,000 for village health teams during surveillance trainings and yet for schools within the same community teachers were not to be paid. The coordination in Kampala Capital City Authority was more complex than other parts of the country, while duty of care was more focused to the field

- Recommendations (in order of impact):

Support the safe continuity of essential health services to women, children, and vulnerable communities:

- Establish a multi-sectoral well, trained UNICEF rapid response team (***)

- Developing a plan and internal UNICEF guidelines for CEHS (***)

- Making available a contingence fund for response (***)

- Integration of the CEHS guidelines into the SBCC engagement (**)

- MDA for malaria during the EVD /and other disease outbreaks (**)

- Integration of Risk communication, CEHS and ICDS and SBCC (joint work plans, trainings, joint activities (*)

Support to households directly affected by EVD including survivors and chronically poor households to meet their basic needs:

- For future public health outbreaks, it is important to include social protection as part of the response.

# Continuity of Learning:

- Integrations of continuity of education services in all emergencies including health in emergencies right from the onset of the response. (***)

- Strengthen duty of care for all response teams. (***)

- Prepositioning of supplies and materials for health emergencies. (***)

- Flexible modalities of cash transfers be consistently done as per the L2 guidance. (***)

- Develop and maintain an updated contingency plan for all possible risks. (***)

- Strengthening Knowledge Management for UNICEF in relation to the response. (**)

- Strengthening data and information management at all levels for government. (**)

- Strengthen the use of the staff roaster for emergency. (**)

staff and not Kampala based response teams.

Summary of recommendations and action plan tracker:

Based on the recommendations from the AAR and to ensure accountability and follow-up, several recommendations have been defined. The recommendations have been included in an action plan tracker with clear actions, responsibilities, and timeline. The action plan tracker will be posted on a shared site with access for all staff and reviewed quarterly during country management team and/or emergency management team meetings or other relevant forum.

|  | Issue | Recommendation | Milestones for implementation of recommendation | Responsible section | Forum | Timeline/ follow up |
| --- | --- | --- | --- | --- | --- | --- |
| Recommendations for internal action: |  |  |  |  |  |  |
| 1. | Limited capacity in implementing L2 procedures and benchmarks for emergency preparedness and response. | Strengthen capacity of staff in all sections in emergency preparedness and response and L2 procedures. As part of this, UCO with support from RO to consider an office wide orientation of the L2 emergency procedures to ensure a common understanding for both programme and operations. As part of the orientation, simplifications of partnerships will be included as well as benchmarks for emergency response in line with the CCCs to deliver as “one office”. | - Liaise with RO on the way forward and how such an orientation can be organized/facilitated. - Plan training (including simulations) in the coming months. - Ongoing follow-up, coaching and mentoring. - Look into other capacity building options such as potential stretch assignments or staff exchanges. | FOE | EMT | August 2023 |
| 2. | Lack of capacity to systematically address public health emergency risks at national level and sub-national level. | Develop an office wide resilience strategy for strengthening public health emergency management systems | - Conduct a public health risks analysis. - Causality analysis - Develop a Theory of Change and define the programmatic strategies. | CSD FOE | CMT | Quarterly |
| 3. | Fragmentation of preparedness plans for different public health risks. | Harmonization of the Emergency Preparedness Plans, through integration of various public health emergency risks including EVD, cholera, Marburg etc. | - Liaise with RO and get the template for PHE. - Start the consultative planning process. | CSD FOE | EMT | Quarterly |
| 4. | Lack of comprehensive continuity plan for the Education section that builds on the gains of the COVID-19 response. | Develop and implement continuity plan aimed at utilizing existing COVID-19 structures in strengthening the education system. This inlcudes using the trained and empowered school health teams (headteacher, teachers and students) and village health teams to strengthen ongoing school health programmes. | - Analyzing the existing documentation and lessons learned during COVID-19 response. - Developing a continuity plan in a consultative manner. | BEAD | EMT | Quarterly |
| 5. | Poor integration of zonal offices in public health emergency response. | Strengthen the role of UCO field offices during public health emergency response. | - Developing SOP outlining the role of the zonal offices in public health emergency response. | FOE | EMT | Quarterly |
| 6. | Need to ensure proper documentation of best practises. | Ensure all best practise from the EVD response are documented and shared with relevant staff in HQ for future public health response (Hubs, innovative ways of using mobile money and training of journalists etc). | - Sections to document best practice FOE to consolidate and share with HARP section in RO. | Section chiefs PME FOE | EMT | Quarterly |
| 7. | Lack of proper integration of operational elements/components in the preparedness planning process. | Ensure UCO implements L2 operational aspects are properly integrated in the preparedness and response planning. This includes HR, supplies, finance, and administration | Sections to ensure operational minimum preparedness standards (MPS) in their preparedness planning and consult operational staff (HR, supply, finance, and admin) in the development of preparedness plans | Section chiefs | EMT | Quarterly |
| 8. | Lack of well capacitated rapid response team for deployment. | Establish a multi-sectoral well trained and equipped UNICEF rapid response team/emergency focal point ready to be deployed. | - Identify staff to be part of the multi-sectoral rapid response team - Provide orientation to the team on public health emergency response | FOE CSD | EMT | Quarterly |
| 9. | Weak duty of care for response staff in Kampala. | Strengthen duty of care for all response teams. | - Extend duty of care package to Kampala Staff during public health emergencies | HR | EMT | Quarterly |
| 10. | Lack of an emergency specific resource mobilization concept notes. | UCO to develop a resource mobilisation plan/concept notes for emergency response including a plan how RO can support UCO and explore funding options during the onset of future emergencies, such as pandemic funds and First Action Initiative. | - PME to develop emergency specific concept notes for each section. | PME Section Chiefs | CMT | Quarterly |
| 11. | Lack of an integrated and costed community engagement package. | Integrated and costed community engagement package. | - Develop and share an integrated and costed community engagement package. | SBC | Section meeting | Quarterly |
| 12. | Fragmented coordination of WASH/IPC pillar(s) - National vs districts and clarify roles and responsibilities within the national pillar | Review coordination structure for WASH/IPC pillar(s) - National vs districts and clarify roles and responsibilities within the national pillar | - Support MOH to assess the current WASH/IPC pillars - Propose harmonization of the pillars - Define roles and responsibilities | CSD (WASH) | MoH National Task Force for Public Health Emergencies | Quarterly |
| 13. | Limited capacity of service providers on MHPSS | Continued capacity strengthening of para-social workers on their role in MHPSS in health emergencies. | - Social service workforce and frontline workers are trained on MHPSS | CP CSD/ Health | EMT | Quarterly |
| 14. | Lack of clarity on roles of each sector within UNICEF on MHPSS | Engagement internally to bring more clarity on where mental health sits within UNICEF. | - Define the roles and responsibilities | Deputy Representative | EMT | By July |
| 15. | Lack of integrated SBC messages inclusive of MHPSS and CP. | Be proactive and develop integrated SBC messages inclusive of MHPSS and CP. | Develop the SBC messages Disseminate the messages | SBC | RCCE-Subcommittee | June 2023 |
| 16. | Lack of capacity among health workers on the deployment of IYCF and RUIF | Capacity building on IYCF and RUIF before prepositioning is required. | Train health workers on the administration of IYCF and RUIF | CSD/ Nutrition | MoH Strategic planning meetings | Quarterly |
| 17. | Lack of internal UNICEF guidelines for CEHS Integration of the CEHS guidelines into the SBCC engagement. | Developing internal UNICEF guidelines for CEHS Integration of the CEHS guidelines into the SBCC engagement. | Develop the guidelines Validate and disseminate the guidelines | CSD/Health | PME EMT | Quarterly |
| 18. | Limited resources to support the recommended two rounds of MDA | MDA for malaria during the EVD /and other disease outbreaks of viral haemorrghic nature. | Plan and provide adequate resources for MDA exercise as it is a costly activity | CSD/Health | MoH Strategic planning meetings | Quarterly |
| 19. | Inconsistencies in the execution of RCCE strategies by partners; low capacity for RCCE amongst partners and district staff, and Low quality reports and under reporting on RCCE | Integration of Risk communication, and Continuity of Essential Health Services (CEHS) and Integrated Child Days (ICDS) SBC to conduct more joint planning and strategy development meetings with cross sectoral teams. | Develop and disseminate community engagement guidelines and advocate for a community engagement budget at all levels. Develop one joint workplan for RCCE between key departments like Health Promotion and Community Health Within UNICEF SBC and CSD should work together to refine the Community Engagement strategy and execution/operational processes. Ensure joint concept development, planning and | Ministry of Health Director of Health Services Section Chiefs for SBC and CSD | MoH National Task Force for Public Health Emergencies | Quarterly |
| Recommendations for external action: |  |  |  |  |  |  |
| 1. | Absence of Child protection, MHPSS and Education under the national continuity of essential services pillar of the national public health emergency response system. | UCO should advocate for the integration of Child protection, MHPSS and Education in all future public health emergencies. | - Advocate/liaise with MoH on the importance of inclusion Child protection, MHPSS and Education. | CSD CP BEAD | CPWG | Quarterly |
| 2. | Lack of disaggregated data in the national information management system for public health emergencies. | UCO should advocate for child disaggregated data in future emergency response. | - Advocate/liaise with MoH to ensure child disaggregated data. | CSD | MoH Strategic planning meetings | Quarterly |
| 3. | Weak UN inter-agency coordination. | UCO should liaise with RC and other UN agencies and decide on how to coordinate future public health emergencies. | - CSD and FOE to ensure the issue is being brought up in the UNCT. | CSD FOE | UN Coordination with RC | June 2023 |
| 4. | Duplication of efforts within UN agencies; failure to respect the designated mandate by UN agency; the need to pool resources (HR and finance) for effective support to the Government | UN RCCE coordination mechanism required. Inter-agency coordination group RC’s office | - Revive the UN Inter – agency technical working groups and meetings - Create a UN-RCCE taskforce where all UN agencies are represented | FOE Deputy Rep - Programme | PMT & EMT | July 2023 |
| 5. | Unnecessary budget splits; inconsistencies in donor reports; the high threat of duplication of efforts and miscommunication with partners. | Advocacy for integrating the RC & CE pillars. | Document and share experiences show the value of integration and coherence of RCCE | UNICEF Representative and SBC Chief | MoH Strategic planning meetings | Dec 2023 |
| 6. | Lack of engagement in the response from MGLSD. | UCO to advocate and work with MGLSD to ensure that in future health emergencies they take a leading role. | UNICEF advocate/provided technical support to MGLSD to ensure that they take lead role in emergency situations and children benefit from prevention and response services through inter-ministerial coordination | CP | CPWG | Dec 2022 |

# Annexes:

Annex A: Workshop agenda, list of participants, minutes, materials produced

Annex B: Presentation of survey results

Annex C: Concept note

Annex D: AAR working group reports and presentations per response area

Annex E: UNICEF Uganda Country Office Ebola virus disease response plan

Annex F: Activation and de-activation of L2

Annex G: L2 Benchmark table and user-friendly summary of information from Ministry of Health

Annex H: UNICEF-WHO Memorandum of Understanding on health emergency

Annex I: Cross-border study six countries

Annex J: UCO list of implemented EVD response interventions

## Annex A – Workshop agenda and list of participants

EVD response AAR workshop, 21 March 2023

Venue: Golf Course Hotel, Plot 64, 88 Yusuf Lule Road, Kampala

Agenda

| Time | Session | Method | Facilitator | Notetaker |
| --- | --- | --- | --- | --- |
| 08:00 – 08:15 | Arrival and registration for participants attending Response Area 1 – Coordination, leadership, and partnerships |  |  |  |
| 08:30 – 09:45 | Response area 1: Coordination, leadership, and partnerships | Group discussion | Margarita Tileva – Deputy Representative Divya Jacob – Chief PME | Anna Ekman – TA Reports Specialist Martha Munch – TA Monitoring and Reports Officer |
| 09:30-10:00 | Arrival and registration for all other participants |  |  |  |
| Scene Setting |  |  |  |  |
| 10:00 - 10:15 | Welcome remarks and key objectives of the AAR by Munir Safieldin | Plenary | Munir Safieldin – Representative |  |
| 10:15-10:45 | Overview/chronology of the EVD response in Uganda | Presentation | Ann Robins - Chief Child Survival & Development |  |
| 10:45-11:15 | Presentation of the key findings from the staff survey, KII | Presentation | Jonathan Gamusi – Monitoring & Evaluation Specialist |  |
| Coffee/Tea Break (15 mins) |  |  |  |  |
| Breakout session for response area discussions - What went well? What could have gone better? |  |  |  |  |
| 11:45-13:30 | Response area 2: Risk communication, social mobilization, community engagement and behaviour change | Group discussion | Miriam Lwanga – Chief SBC (ai) | Abdel Asiimwe – SBC Officer |
|  | Response area 3: WASH and IPC in institutions and community | Group discussion | Jonathan Hunter – WASH Manager | Seungwoo Nam – Health Specialist |
|  | Response area 4: Case management | Group discussion | Vedasto Nsanzugwanko – Chief Child Protection | Charles Sevume – Child Protection Officer |
|  | Response area 5: Prevent and address the indirect impact of the outbreak and minimize the negative human and socio-economic consequences | Group discussion | Ann Robins - Chief Child Survival & Development George Gena Ogwang – Education Officer | Martin Ngolobe – Health Specialist Night Stella Candiru – Education Specialist |
| 13:30-14:30 | Lunch Break |  |  |  |
| 14:30-16:00 | Presentation and Feedback from the different pillars | Plenary | All | Anna Ekman – UCO, TA Reports Specialist |
| 16:00-16:15 | Coffee /Tea Break |  |  |  |
| 16:15-17:15 | Discussions/Next steps | Plenary | Divya Jacob – Chief PME |  |
| 17:15-17:30 | Wrap up and closure | Plenary | Margarita Tileva – Deputy Representative |  |

List of participants

| Participant and section |  | Response area |
| --- | --- | --- |
| Representative’s Office |  |  |
| 1 | Munir El Safieldin, Representative | Coordination |
| 2 | Anna Ekman, Reports Specialist | Notetaker |
| Deputy Representative’s Office |  |  |
| 3 | Margarita Tileva, Dep Representative | Coordination |
| 4 | Sarah Achiro, Programme Specialist (Gender/PSEA) | GBV/PSEA |
| Field Operations and Emergency |  |  |
| 5 | Irene Nabisere, Emergency Officer | Coordination/Notetaker |
| 6 | Christopher Ngwerume, Emergency Specialist | Coordination |
| 7 | Stella Ogalo, PM Officer | Coordination |
| Child Survival and Development |  |  |
| 8 | Ann Robins, Chief CSD | Coordination/Continuation of Essent Serv |
| 9 | Chimwemwe Msukwa, HSS Specialist | RCCE |
| 10 | Stephen Mucunguzi, Health Specialist | Coordination/RCCE |
| 11 | Atnafu Getachew Asfaw, Health Manager | Coordination/IPC |
| 12 | Martin Ngolobe, Health Specialist | Coordination/ Continuation of Essent Serv |
| 13 | Zakaria Fusheini, Nutrition Manager | Case Management |
| 14 | Alex Mokori, Nutrition Specialist | Case Management |
| 15 | Amos Ndungutse, Nutrition Specialist | Case Management |
| 16 | Jonathan Hunter, WASH Manager | WASH/IPC |
| 17 | Paul Kejira, WASH Specialist | WASH/IPC |
| 18 | Barbara Asire, HIV/AIDS Specialist | Coordination/ Continuation of Essent Serv |
| 19 | Fred Kagwire, Health Specialist | Continuation of Essent Serv |
| 20 | Flavia Mpanga, Health Specialist | Continuation of Essent Serv |
| 21 | Immaculate Athhire, TA Health Officer | IPC |
| 22 | Sarah Achen, Health Officer, Mbara office | IPC |
| Education |  |  |
| 23 | George Gena, Education Officer Emergency | Coordination/ Continuation of Essent Serv |
| 24 | Night Stella Candiru, Education Specialist | Continuation of Essent Serv |
| 25 | Nada Elattar, ECD Manager | Continuation of Essent Serv |
| 26 | Daphne Mugizi, ECD Specialist | Continuation of Essent Serv |
| 27 | Shariff Kigundu, EiE Officer | Continuation of Essent Serv |
| 28 | Dennis Okulle Ogang, Education Officer, Mbarara | Continuation of Essent Serv |
| Planning, Monitoring and Evaluation |  |  |
| 29 | Divya Jacob, Chief PME | Coordination |
| 30 | Jonathan Gamusi, M&E Specialist | Coordination/Continuation of Essent Serv |
| 31 | George Ebong, Planning Specialist | Coordination/Case Management |
| 32 | Scholastic Adong, M&E Specialist | Coordination/WASH/IPC |
| 33 | Kutloano Leshomo, Reports & Donor Relations Specialist | Resource Mobilization |
| 34 | Martha Munch, Monitoring and Reports Officer | Notetaker |
| 35 | Sophie Zalwango, Senior Programme Associate | Coordination/Notetaker |
| 36 | Diana Nkwanzi, Administrative Assistant | Notetaker |
| Child Protection |  |  |
| 37 | Vedasto Nsanzugwanko, Chief Child Protection | Coordination/Case Management |
| 38 | Lisa Zimmerman, Child Protection Specialist | Case Management |
| 39 | Harriet Nambassa Kajubi, CP Officer | Case Management |
| 40 | Augustine Wassago, Child Protection Specialist | Coordination/Case Management |
| 41 | Irene Oluka, Child Protection Officer | Coordination/Case Management |
| 42 | Nikolaas Swyngedouw, Child Protection Officer | Case Management |
| 43 | Maryam Enyiazu, Child Protection Specialist | Coordination/Case Management |
| 44 | Mystica Acheng, Child Protection Specialist | Case Management |
| 45 | Charles Sevume, Child Protection Officer | Case Management/Notetaker |
| Operation Support to Programmes |  |  |
| 46 | Patrick Mutombo, ICTD Manager /Deputy Rep OPs (ai) | Logistics, Operational Support, and Supplies |
| 47 | Frank Asiimwe, Snr Logistics Assistant | Logistics, Operational Support, and Supplies |
| 48 | Alex Ataali, Transport Associate | Logistics, Operational Support, and Supplies |
| 49 | Berhan Ayenew, Finance Manager | Logistics, Operational Support, and Supplies |
| 50 | Joseph Lubega, Finance Officer | Logistics, Operational Support, and Supplies |
| 51 | Catherine Ayado, HR Officer | Technical Assist. & Cross-sectoral expertise |
| 52 | Moses Karamagi, Driver | Logistics, Operational Support, and Supplies |
| 53 | Gabriel Bako, Administrative Manager | Logistics, Operational Support, and Supplies |
| Mbarara/Gulu Field Office |  |  |
| 54 | Phillips Limlim, Chief FO | Coordination |
| 55 | Susan Birungi Nyakoojo, Emergency Office | Coordination |
| 56 | Abel Asiimwe, SBC Officer | RCCE |
| 57 | Mystica Acheng, Child Protection Specialist | Case Management |
| 58 | Rabin Drabe, Health Specialist | Continuation of Essent Serv |
| 59 | Peter Opwanya, WASH Specialist, Mbarara | WASH/IPC |
| Social Policy and Advocacy |  |  |
| 60 | Tawanda Chinembiri, Social Policy Manager | Continuation of Essent Serv |
| Social Behavioral Change |  |  |
| 61 | Douglas Lubowa, SBC Specialist | Coordination/RCCE |
| 62 | Tabley Bakyaita, SBC Emergencies consultant | RCCE |
| 63 | Miriam Lwanga, Chief SBC (ai) | RCCE |
| 64 | Catherine Ntabadde, Communications Specialist | Communication and Advocacy |
| 65 | Loy Dhikusooka, SBC Officer | RCCE |
| 66 | Gemma Namuleme, Programme Associate | Rcce |
| ESA Regional Office |  |  |
| 67 | Joan Kipwola, Emergency Specialist | Coordination |
| 68 | Edna Moturi, RO, Health Specialist | Continuation of Essent Serv |
| 69 | Sergiy Prokhoriv – RO, SBC Specialist | RCCE |

## Annex B - Concept Note for the After-Action Review (AAR) UNICEF’s response to the Sudan Ebola Virus Disease SDV Outbreak in Uganda

Annex C: Online survey questionnaires, key informant interview questions and presentation of survey results

Online Staff Survey questionnaire

Key Informant Interview questions

Presentation of survey results

Annex D – AAR working group reports and presentations per response area

Annex E - UNICEF Uganda Country Office Ebola virus disease response plan

## Annex F – Activation of L2 and deactivation of L2

# From: Deputy Executive Director-Programmes <ded-programmes@unicef.org> 
Sent: Saturday, October 29, 2022 6:27 AM
Subject: Activation of UNICEF Corporate Emergency Level 2 Scale-up Procedure for the Ebola Outbreak in Uganda - from 27 October 2022 to 26 April 2023

Dear colleagues,

# On 20 September 2022, Uganda declared an Ebola outbreak of the Sudan strain (Sudan Virus Disease, SVD) following a confirmed case in Mubende district. By 22 October 2022, 90 cases including 48 deaths (28 confirmed, 20 probable) were reported in seven affected districts: Mubende, Kassanda, Kyegegwa, Bunyangabu, Kagadi, Kampala and Wakiso.

# The epicentre of this outbreak (Mudembe district) is approximately 2 hours away from the capital in an area of high population movement, intensifying the risk of further spread if the outbreak is not controlled in the early stages. Ebola is a serious, often fatal disease in humans and the lack of approved vaccine and therapeutics for the Sudan strain represents an additional challenge in curbing this outbreak.

The combination of a highly mobile population, inadequate contact tracing and Infection Prevention Control (IPC), and traditional practices that can amplify transmission mean there is a high risk of SVD spreading within Uganda and beyond the borders of Uganda.

UNICEF response in Uganda started immediately following the declaration of the outbreak and focuses on coordination, IPC/WASH, Risk Communication and Community Engagement (RCCE) and case management, including nutrition for children admitted in Ebola Treatment Units, Mental Health and Psychosocial Support (MHPSS) and continuity of essential health and social services.

# Considering the involved risks, UNICEF will apply a no-regrets approach for this response scale-up, acknowledging that any delays in the availability of resources will elevate the risk of spread. I have, therefore, approved the recommendation by Mohamed Malick Fall, ESA Regional Director and endorsed by Manuel Fontaine, EMOPS Director, to activate a Level 2 (L2) Corporate Emergency Activation Procedure (CEAP) Scale-up for the Ebola outbreak in Uganda. In alignment with UNICEF’s commitment to Prevention of Sexual Exploitation and Abuse (PSEA), specific PSEA measures will be implemented and scaled-up from the onset of the L2 activation with the mobilization of dedicated support.

ESARO will coordinate the support required for the implementation of this L2. The UNICEF Representative in Uganda, supported by an Ebola coordinator leading the Ebola Response Team, will remain accountable for the response in country. EMOPS and the Public Health Emergencies Team in PG will work in close collaboration with ESARO and other Headquarters (HQ) Divisions to provide the support required by the affected country offices.

Recognizing the progress made in strengthening preparedness for Ebola and implementation of measures to mitigate the risk of potential spread in the neighbouring countries during past outbreaks, ESARO and WCARO will continue to actively engage with Country Offices in the regions to ensure their readiness to support prevention efforts and respond quickly to a potential SVD spread. This L2 CEAP Ebola activation will factor the high risks of cross-border spread and can be immediately extended to any other country that confirms a SVD case.

I am thankful for the commitment and dedication of all our colleagues in Uganda and the region who continue to deliver lifesaving assistance to affected and at-risk communities.

Warm regards.

Omar Abdi

# From: Deputy Executive Director-Programmes <ded-programmes@unicef.org> 
Sent: Thursday, April 20, 2023 7:19 PM
Subject: Deactivation of UNICEF Corporate Emergency Level 2 Scale-up Procedure for the Ebola Outbreak in Uganda

Dear colleagues,

Six months ago, in October 2022, UNICEF activated its Corporate Emergency Level 2 Scale-up Procedure in Uganda, following the declaration of an Ebola outbreak of the Sudan strain (Sudan Virus Disease, SVD) by the Ugandan Ministry of Health on 20 September 2022. The L2 activation in Uganda enabled the country office to quickly scale up the response through access to Emergency Preparedness Funds (EPF), surge deployment from RO and HQ, strengthened PSEA-related interventions and support on partnerships, addressing supply needs, continued advocacy, and resource mobilization.

With no vaccines and therapeutics, and with cases reported in major urban centres such as Kampala and Jinja, this was one of the most challenging Ebola outbreaks of the past years. Despite the many challenges, on 11 January 2023, less than four months after the first case was confirmed, the outbreak was declared over. In total there were 164 cases (142 confirmed and 22 probable) and 55 confirmed deaths in 9 affected districts.

UNICEF’s response in Uganda started immediately following the declaration of the outbreak and focused on coordination, IPC/WASH, Risk Communication and Community Engagement (RCCE), case management and Mental Health and Psychosocial Support (MHPSS). Based on lessons learned from previous outbreaks, UNICEF also maintained a strong focus on continuity of essential health and social services. In collaboration with WHO, UNICEF supported the Ministries of Education and Health to develop and implement guidelines for safe school operations and continuation of learning during the outbreak, and schools have remained opened. UNICEF also supported the MoH and partners to ensure the continuity of primary health care services during the outbreak, including nutritional services, pre and postnatal care, HIV and immunization. This was achieved by ensuring the availability of essential supplies and presence of community health workers and coordination mechanisms established during the COVID-19 response.

Following the official declaration of the end of the Ebola outbreak, a follow-up programme has been put in place to support survivors. Neighbouring countries remain on alert and are encouraged to continue strengthening their capacities to detect and respond to infectious disease outbreaks. Uganda CO developed a post-Ebola Response Plan covering a six-month period (Jan to June 2023). In line with MoH priorities and leveraging UNICEF’s comparative advantages, the CO continues to support the country in maintaining its capacity to respond quickly to any flare-ups. After-Action Reviews have also taken place to document the best practices of the response.

Due to the improved situation and increased capacity to respond to any eventual flare-up, I have approved the recommendation by Mohamed Malick Fall, ESARO Regional Director and endorsed by Manuel Fontaine, EMOPS Director, to deactivate the Level 2 Corporate Emergency Activation Procedure (CEAP) for Uganda.

I am thankful for the commitment and dedication of all our colleagues and partners who have delivered and will continue to provide lifesaving assistance to much-needed women and children in Uganda.

Warm regards.

Omar Abdi

Deputy Executive Director, Programmes

## Annex G: UCO Response Plan Performance Dashboard and Ministry of Health information in user-friendly format

Annex H - UNICEF-WHO MoU on health emergency

## Annex I – UNICEF ESARO Ebola Virus Disease Preparedness and Response in Priority Eastern and Southern Africa Countries 2018-2020

Annex J – UNICEF Uganda Country Office Ebola virus disease (EVD) response plan activities implemented during 20 September 2022-11 January 2023

UNICEF Uganda Country Office Ebola virus disease (EVD) response plan activities implemented during 20 September 2022-11 January 2023

On 20 September, the Government of Uganda declared an outbreak of Ebola Virus Disease (EVD) following a confirmation of a case in Mubende District. UNICEF’s EVD response plan was aligned with the Government’s response plan and included the following response areas:

Response area 1: Coordination, leadership, and partnerships

Response area 2: Risk communication, social mobilization, community engagement

Response area 3: Surveillance and contact tracing community

Response area 4: Water, Sanitation, and Hygiene Promotion (WASH)

Response area 5: Case Management

Response area 6: Prevent and address the indirect impact of the outbreak

Response area 7: Logistics and Operational Support

By 11 January, after 113-days, the outbreak was declared over with a cumulative 142 confirmed cases and 55 deaths in nine affected districts (Mubende, Kassanda, Kyegegwa, Bunyangabu, Kagadi, Masaka, Kampala, Wakiso and Jinja). UNICEF’s support to the EVD response was substantial and all interventions are listed below:

Response area 1: Coordination, leadership, and partnerships

Internal coordination

- Establishment of four hubs in high-risk areas (Mubende (covering Kassanda), Kampala, Jinja and Masaka)

- Bi-weekly EMT and regular TET meetings chaired by the Representative including all staff involved in the response.

- Visit by the Regional Director to inform the RO on the situation

- Daily reports from the field.

- Daily updates of the dashboard and information from the Ministry of Health.

External coordination

- High level member in the Strategic management committee (SMC).

- Pivotal technical role in the National and sub-national taskforce (NTF) including coordination, harmonization, and collaboration among implementing partners.

- Participated and provided technical support to the Incident management team (IMT) including pillar and sub-pillar committees.

- Participated and provided technical support to the district task force (DTF) by technical leads in the field.

- Co-Chair of the Risk communication pillar together with the Ministry of Health, Commissioner health services health promotion, education, and communication department

- Member of the Community engagement pillar

- Member of the Water sanitation and hygiene pillar

- Member of the Infection prevention and control sub-pillar

- Member of the Surveillance pillar

- Member of the Clinical sub-pillar

- Member of the Mental health psychosocial support (MHPSS) sub-pillar

- Member of/and provided leadership in the coordination of nutrition response in the National taskforce (NTF)

- Co-chair the Continuity of essential health services sub-pillar with the Ministry of Health

- Member of the SIRI Pillar

- Observer in the Scientific advisory committee

- Member of the Logistics sub-committee

- Supported District task force and District disaster management committees (DDMC) on preparedness and response.

- Provided input to the partners 4Ws matrix.

- Raised resources based on the Ministry of Health “National Ebola virus disease plan”.

# Provided technical support from GOARN to support the establishment of an IOA cell.

# Provided space for the IOA cell on behalf of the Ministry of Health at IDI.

# Provided rapid integrated analyses to the Ministry of Health to better understand outbreak dynamics and their impact on communities.

Response area 2: Risk communication, social mobilization, community engagement

Mass media messaging

- 5,9 million people reached with accurate, cultural, and gender-appropriate messaging on EVD prevention, early treatment and access to services, through mass-media messaging support to 29 radio stations and 8 TV stations.

# Social media monitoring to provide feedback to the risk communication and other pillars for action.  U-Report was used to share key EVD information through polls and live conversations through the Ebola chatbot.

# UNICEF has printed information education communication materials for a value of US$235,918 and distributed them to all affected districts and those at high risk for risk communication.

Mobilization of key influencers

# Oriented and engaged with 56,649 key influencers on Ebola prevention, resulted in 1,036,547 people participated in community dialogue meetings, which were conducted to raise awareness on EVD prevention and control.

Community engagement

# 1,130 village health teams and local council member trained on risk communication and safe and dignified burials. 1,044 megaphones were distributed to affected districts to enable mobilization and communication at mass gatherings.

# UNICEF, in partnership with Ministry of Health, oriented 510 traditional healers from 9 affected districts on Ebola, aimed at promoting awareness on the early referral of their clients with Ebola-like symptoms to health facilities.

# 1,558,094 people of different age groups and profiles shared their concerns and asked questions through established feedback mechanisms through community meetings (off-line) and social listening, media monitoring, the Ministry of Health Call Center and U-Report (online).

# Supported development of a comic book targeting children and adolescents.

# 5 staff deployed in Kassanda, Kampala, Wakiso, Jinja, and Masaka to oversee implementation of community engagement activities.

# Supported the deployment of 5 Ministry of Health staff who worked in collaboration with the districts to establish taskforces, resulting in over 3,415 village taskforces were activated, 80 parish taskforces, 4 municipal and 10 division taskforces activated.

# 5 full-time vehicles were hired to support community engagement activities in five districts with deployed staff.

# 6,500 businesses reached with EVD risk communication materials.

Systems strengthening

# 10 Social behaviour change officers were recruited and deployed to provide technical support to districts to support coordination of risk communication and community engagement interventions in the district, including 10 hired and deployed vehicles to support the implementation.

# 625,570 people have been reached through engagement actions (community dialogues) conducted to raise awareness on EVD prevention and control.

# Supporting the ongoing anthropological study under risk communication and community engagement.

Vaccinations

- No vaccine was available during the response.

Media training at national and regional levels

# 21 Kampala-based editors and 337 journalists/editors nationwide oriented on accurate, responsible, and ethical reporting to curb fake news and misinformation.

Private Sector Engagement

- The Private Sector Engagement unit provided private sector partners with soft copy versions of IEC materials which were distributed to estimated 6,450 businesses in Uganda.

Response area 3: Surveillance and contact tracing

# 15 vehicles deployed to strengthen alerts management, active case search for EVD and support data collection.

# 1 technical officer deployed to support Ministry of Health and WHO with the Go data application for data collection as provided from Headquarters through Global outbreak alert and response network (GOARN).

# Procured infection prevention and control water, sanitation, and hygiene supplies (IPC/WASH) for village health teams  for a value of US$ 230,000 to support community surveillance for EVD suspected cases.

# Provided 10 computer tablets to the Ministry of Health to support data collection.

Response area 4: Water, Sanitation, and Hygiene Promotion (WASH)

# Support for infection prevention and control in Ebola affected communities

# Supported payment of allowances to burial teams and selected Government staff in line with the level of payments to various categories of staff/responders.

# 16 vehicles were provided to the trained EVD burial teams for safe and dignified burial and control of further transmission of Ebola in Kassanda (6) and Mubende (10) Districts.

# 4,176 health care staff, including village health teams, supported with capacity building on infection prevention and control.

# All health facilities and schools in Mubende and Kassanda assessed in terms of water, sanitation, and hygiene services.

# Financial assistance given to Ministry of Health - Environmental health department to train health workers on infection prevention and control through water, sanitation and hygiene standards and water, sanitation, and hygiene facility improvement tool (FIT) approach to improve infection prevention and control in institutions.

# 50 directly affected households and 24 health facilities supported with critical infection prevention and control/water, sanitation, and hygiene supplies in Kassanda district through the ring approach.

- 57 affected and at-risk districts supported with infection prevention and control/water sanitation and hygiene, risk communication, and nutrition supplies worth US$757,461.

# Provision of essential WASH supplies and equipment

# Upgraded the water supply systems using solar motorization in five health facilities in Kiyuni, Butologo health centre III and St. Joseph Madudu health centre III in Mubende District, Kalwana Ebola treatment unit in Kassanda District and Jinja regional referral hospital and Maga Maga health centre III in Jinja District.

# Supported Mubende Ebola treatment unit with tanks to provide 70,000 litres of water storage. One 10,000 litre tank was connected to the National Water grid to provide a water supply to the Ebola treatment unit located within Mubende regional referral hospital.

# Provided financial assistant to Ministry of Health to conduct WASH assessments. In total, 372 health facilities, both government and private and over 200 schools with focus on Mubende and Kassanda Districts were assessed.

# Supported the safe re-opening of schools through distribution of critical WASH supplies to 330 schools and 336 health facilities and promoted infection prevention and control among health care workers.

# 40 health facilities and 38 schools in Mubende District were provided with WASH supplies.

# 24 health facilities and 50 households affected by EVD were supported with hygiene items and disinfectants in Kassanda District.

# Provided financial assistance to train health workers and teachers to adhere to infection prevention and control standards. In total 1,466 health workers benefited, and 254 teachers were trained in EVD affected districts.

# 38 non-functional handwashing facilities in Mubende District with focus on public places and high-risk areas were rehabilitated.

# Supported Mubende regional referral hospital with the repair/rehabilitation of the electric incinerator for proper waste management.

Response area 5: Case management

- Nutrition

Building the capacity of the district, health facility, and community manager and service providers in IYCF and nutrition in the context of Ebola

# 863 health workers (including frontline and managers) trained on nutrition and infant and young child feeding.

# 64,901 primary caregivers counseled and educated on appropriate “infant and young child feeding”. Specifically, 75 mothers who had stopped breastfeeding due to Ebola viral disease were supported to re-lactate through continuous infant and young child feeding counseling and support by health workers and psychosocial team.

# Supported the development, printing, and dissemination of 1,490,333 standard operating procedures (SOPs) and guidelines on nutrition in response to EVD to the nine EVD affected districts.

# Support access and availability of essential nutrition supplies and commodities for EVD response

# 15,312 packages of ready-to-use-infant-formula (RUIF) was procured and pre-positioned. A total of 79 infants affected by Ebola were supported with RUIF in the affected districts. Additional 57,825 packages are in the pipeline.

# 165,945 children 6-59 months received nutrition assessment using mid-upper arm circumference method (MUAC) in districts affected by Ebola as part of continuity of essential nutrition services.

# 1,491 children identified with acute malnutrition received appropriate care and management according to the national integrated management of acute malnutrition (IMAM) protocol.

- MHPSS and child protection

# Support MHPSS services for EVD-affected individuals and families, including children in ETUs and communities and survivors

# Advocated and worked closely with community-based services departments, including the probation and social welfare and community development officers in all affected districts to ensure the inclusion of protection considerations in all aspects of the EVD response.

# 492 psychologists/psychiatrists, health workers and community structures (village health teams/para social workers) were trained and deployed to Ebola treatment and isolation units and communities to provide mental health and psychosocial support to ensure adequate MHPSS services. As a result, 16,359 children and 4,671 caregivers received mental health and psychosocial support.

# 3,807 individuals reached with sensitization on child protection and mental health and psychosocial support issues to prevent violence against children by risk communication and community engagement interventions.

# Support protection services, including interim care and foster care for EVD-affected children

# 129 child survivors of violence were reached with critical child protection case management services. In addition, 15 children temporarily separated from caregivers and families benefitted from alternative care services, including placement in foster families.

# A child-friendly Ebola treatment unit guidance document was developed and provided practical guidance to health workers in Ebola treatment units on ensuring the protection of children.

# 111 Play kits for children of different age groups was provided to isolation sites and Ebola treatment units and administered by mental health and psychosocial support teams in close collaboration with district community service department.

# 102 people responding to EVD from district local government, civil society organizations (CSOs), cultural and religious leaders have been trained on how to report allegations on sexual exploitation and abuse.

# 5,263 children and adults had access to a sexual exploitation and abuse reporting channel.

# 594 women, girls and boys received gender-based violence risk mitigation, prevention, or response interventions.

# Provided critical child protection case management services, including alternative care.

# Provided community-based psychosocial support.

# Raised awareness and sensitization on child protection risks in EVD contexts.

# Training and orientation of health and social welfare structures on protection of children in EVD contexts.

# Inclusion of protection from sexual exploitation and abuse (PSEA) and gender-based violence (GBV) risk mitigation measures in public health emergencies (PHEs), including allocating dedicated resources.

# Care services for survivors of gender-based violence as well as for women and children at risk.

# Ensured safe and accessible facilities and services for women and children.

# Provision and/or establishment of safe and accessible sex-segregated facilities.

# Integrating messages on protection risks, services for survivors, for women and children at risk, and how to access the available services.

Response area 6: Prevent and address the indirect impact of the outbreak

# Support the safe continuity of essential health services to women, children, and vulnerable communities

# Provided financial and technical support for the development of a guideline for management of pregnancy, labor, and delivery with EVD.

# Provision of 17 high performance tents to Mubende, Kassanda, Hoima Regional Referral Hospital, Kampala region, Mukono District (Goma health centre IV and general hospital) and Mulago Referral hospital, including water system and infection prevention and control support to avoid decongestion and to maintain primary health care including integrated community case management (malaria, pneumonia, and diarrhea) and nutrition.

# Provided protective gloves for infection prevention and control/personal protective equipment supplies to ensure continuity of essential health services for Masaka regional referral hospital.

# Supported the Malaria Consortium with reaching 181,985 people with mass-drug administration for malaria.

# 9.7 million children (95 per cent coverage) reached with Polio R2 nOPV vaccine.

# Support to households directly affected by EVD including survivors and chronically poor households to meet their basic needs

# Integrated study conducted to understand the dynamics between an EVD outbreak and response on sexual, reproductive, maternal and child health service access.

# Integrated study to understand health care workers knowledge, behavior and practices was conducted in Kampala.

# Extending support to Makerere university to lead a study on the socioeconomic impact assessment of EVD together with the Office of the Prime Minister.

# Continuity of Learning

# Supported Ministry of Health’s school health team and Ministry of Education and Sports to develop and disseminate EVD standard operating procedures, job aides, guidelines for safe operation of schools, safe release of learners from districts with restrictions.

# 3,345 infra-red thermometers provided to schools to strengthen school level screening.

# Conducted training of trainers for 213 teachers on school-based management and response to EVD and related health epidemics in five districts.

# 2,170 teachers and non-teaching staff were oriented on EVD prevention, early treatment seeking and notification.

# Over 12,468 primary leaving examinations candidates within Mubende, and Kassanda Districts were provided with home learning materials for learners in home isolation.

# 5,185 learners were transported into and out of Mubende and Kassanda Districts.

# Facilitated 30 primary leaving examinations candidates in home isolation in Rubaga Division to sit for their examinations.

# Supported 140 learners in home isolation with learning materials and facilitated their reintegration back to school.

# 283 schools in high-risk sub-counties/ring received training on EVD prevention in school.

# 3,226 schools in 7 very high-risk districts were supplied with copies of Standard Operating Procedures and Guidelines for EVD prevention in schools

# 191 schools in high-risk sub-counties were supported with at least one supervisory visit from the Ministry of Education and Sports/District Education Offices.

# An assortment of learning materials and relevant textbooks were distributed to two EVD affected schools in Rubaga division, Kampala including psychosocial support for teachers and learners.

Response area 7: Logistics and Operational Support

- Contributed to the central coordination of quantification of supply needs, identification of gaps and allocation of orders to different warehouses and partners.

# 1 logistics officer was deployed to Mubende District to provide support to the Mubende and Kassanda Districts stores, including strengthening the stock management, monitoring, reporting, as well as information flow between the response pillars, the logistics team, and the district taskforce.

# Provided infrastructure for the emergency treatment units in Kassanda, Mubende and Mulago in partnership with MSF, focusing on tents for isolation and necessary water, sanitation, and hygiene infrastructure.

In addition to the 142 confirmed cases, there were 22 probable cases (9 children and 13 adults). Initially, the Government included the probable cases in the reporting but later dropped it since the cases were never confirmed. WHO is still mentioning the probable cases in their overall reporting on the EVD outbreak Ebola outbreak 2022 - Uganda (who.int) . Depending on the inclusion of the probable cases or not the CFR changes.

Overall cases (adults and children): Confirmed cases: 142, confirmed dead: 55 – CFR: 39%

Confirmed cases: 142 + probable cases: 22 = 164 cases, confirmed dead: 55 + probable cases: 22 (all dead) = 77 – CFR: 47%

Children: Confirmed cases: 28, confirmed dead: 12 – CFR: 43%

Confirmed cases: 28 + probable cases: 9 = 37 cases, confirmed dead: 12 + probable cases 9 = 21 – CFR: 57%

Adults: Confirmed cases: 114, confirmed dead: 43 – CFR: 38%

Confirmed cases: 114 + probable cases: 13 = 127, confirmed dead 43 + probable cases 13 = 56 – CFR 44%

New World Bank country classifications by income level: 2022-2023

GDP per capita (current US$) - Uganda | Data (worldbank.org)

Other supplies were dispatched straight from the suppliers, and not captured in the US$ 885,000 warehouse figure.

posters, leaflets, banners, job aides, brochures, fact sheets, question & answer booklets

teachers, local leaders, traditional leaders, religious leaders, local council leaders, traditional healers, uniformed/security personnel, boda-boda cyclists

An outbreak investigation tool for field data collection during public health emergencies including for case investigation, contact follow-up, visualization of chains of transmission and secure data exchange.

including gumboots, hand sanitizers, reusable aprons, village health team referral books, heavy duty gloves and face shields

# as outlined in the Circular on Renumerations of the Health workers engaged by partners in the National Response against Ebola Outbreak issued by the Ministry of Health on 9th November 2022.

including commercial buildings, public transport stations and markets

Presented to the Continuity of Essential Health Services pillar for action

Presented to the IPC/WASH pillar for action

Médecins Sans Frontiers