## Slide 1
23 August 2023
GNC Partners Call
Emergency Nutrition Response in Sudan
Notes: Insert map of the country with affected areas/districts or photos

## Slide 2: Partner Call Agenda
Welcome and Introduction (5 minutes)
Update from Sudan Coordination team (30 minutes)
UNHCR update on Sudan and refugee situation and response (15 minutes)
Q&A (15 minutes)
Next Steps and Wrap-up (5 minutes)

## Slide 3: Sudan update
Situation: General overview and the Nutrition situation in particular (using available data & recent SMART surveys results)
Response strategies: current achievements & gaps
  Geographical and treatment coverage
  Reporting rate
  Sudan NC developed different response scenarios and key programs shifts
  Updates on using the simplified approaches in the management of wasting under Sudan response
  Coordination with UNHCR at country office level
Partners operational presence and factors affecting that
Nutrition supplies pipeline status
Funding gaps
Sudan nutrition cluster information platforms & Sudan Nutrition Cluster capacity enhancement
Challenges
Upcoming priorities

## Slide 4
1a) Nutrition Situation in Sudan prior to Conflict
Recent SMART surveys: Mar 2023
Kalemando- ND:
GAM 20.6% and SAM 4.8%
Reif Al Shergi-SK
GAM 10.9% and SAM 1.3%
MUAC screening results
  Refugees
  Communities
Stunting: 36%
Anaemia U5: 48%
Dietary Diversification: 25%
EBF: 62%

## Slide 5: 1b) Current Acute Malnutrition Situation
3.4 million children aged 6-59 months acutely malnourished. This includes over 690,00 children severely malnourished.
IN NEED OF TREATMENT
1 million pregnant and breastfeeding women and girls (PBW/G) acutely malnourished.
IN NEED OF TREATMENT
The revised Humanitarian Response Plan (HRP) in May 2023 projected a
30% increase in the caseload of acute malnutrition in hotspot areas of Khartoum, Darfur, and Kordofan states.
15% increase in the caseload of acute malnutrition in IDP hosting localities.
10% increase in the caseload of acute malnutrition in the rest of the country.
PIN increased by 13% from 3.99M to 4.52M
SAM PIN increased by 13% from 611,556 to 690,677
PIN for SAM inpatient increased from 90,000 to 103,598
MAM PIN increased by 13.3% from 2.44M to 2.77M

## Slide 6: Nutrition situation: IPC Acute Food Insecurity June 2023 - February 2024
  Over 20.3 million people, representing 42% of the population, increased by 74% from 11.7M to 20.3M when compared to the same period from last year’s projection
  About 96% of acute malnutrition caseload (SAM and MAM) live in localities with IPC-AFI phase 3 (66%) and 4 (30%)
  The eight states in Darfur, West and South Kordofan and Khartoum
    Over 40 percent of the population is projected to suffer from acute food insecurity
    About half (50%) of the national caseload of acute malnutrition live in those 8 states
Decline in Food security
Decrease in the availability and accessibility of nutritious and diverse food
Increased malnutrition vulnerable children, pregnant women, and breastfeeding women and girls

## Slide 7
Chart: U5 SC SAM
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Y2020 | 2498 | 1228 | 1208 | 1157 | 1320 | 2729 | 3175 | 3014 | 3391 | 2949 | 1875 | 1342
Y2021 | 1896 | 1660 | 1728 | 1869 | 2508 | 3662 | 2833 | 3644 | 4008 | 2910 | 2252 | 2029
Y2022 | 2058 | 1785 | 1843 | 2170 | 3644 | 3808 | 3364 | 4130 | 5097 | 3863 | 2623 | 2266
Y-2023 | 1506 | 1375 | 1487 | 1283 | 1728 | 1731 | 3224
Chart: U5 SAM OTP
| Jan | Feb | Mar | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Y-2023 | 21013 | 20540 | 19485 | 12719 | 19082 | 21975 | 25927
Y-2021 | 16707 | 15426 | 18179 | 17695 | 20431 | 31883 | 22003 | 25587 | 29227 | 23305 | 21392 | 18924
Y-2022 | 22219 | 18941 | 20328 | 21678 | 27970 | 35885 | 28250 | 36378 | 34766 | 28156 | 25041 | 22001
Y-2020 | 17906 | 18984 | 17669 | 17284 | 16757 | 26019 | 28117 | 21727 | 28187 | 27053 | 20727 | 16602
Chart: U5 MAM
| JAN | FEB | MAR | Apr | May | Jun | Jul | Aug | Sep | Oct | Nov | Dec
Y-2020 | 13761 | 17640 | 23717 | 24487 | 21794 | 35043 | 34065 | 30068 | 34797 | 34089 | 25957 | 19878
Y-2021 | 16439 | 25547 | 42421 | 42074 | 44163 | 68394 | 49828 | 56783 | 75968 | 65830 | 56098 | 53088
Y-2022 | 62235 | 69785 | 58351 | 55591 | 62590 | 67925 | 79277 | 85884 | 75234 | 59449 | 49088 | 59591
1d) Admissions Trends 2020-2023

## Slide 8: Nutrition situation: New Admission Trends Analysis
Chart: Trend Analysis for AMVO Supported OTPs in Khartoum State (JAN to JUN 2023)
| Jan | Feb | March | April | May | June
Bantiue | 52 | 35 | 41 | 18 | 120 | 124
Mayo/Mandela | 50 | 91 | 73 | 35 | 160 | 200
Dar Elnaeim | 80 | 68 | 63 | 70
Chart: Trend Analysis for AMVO Supported OTPs in East Darfur State (JAN to JUN 2023)
| Jan | Feb | March | April | May | June
Algogan | 5 | 10 | 8 | 15 | 9 | 30
Alaied | 57 | 60 | 36 | 37 | 57 | 83
Abuseinadera | 57 | 63 | 48 | 48 | 61 | 95
Fare Elhabi | 17 | 17 | 19 | 13 | 19 | 28
Chart: Trend analysis for RI Zamzam A OTP in North Darfur
| January | February | March | April | May | June
ZamZam A 2022 | 24 | 44 | 39 | 35 | 58 | 135
ZamZam A 2023 | 22 | 53 | 61 | 1 | 108 | 208
Reports of increased admissions in partners operational areas
Chart: Admission Trend Albuluk SC Khartoum 2022- 2023
| Jan | Feb | Mar | April | May | June | July
2022 | 22 | 15 | 22 | 21 | 51 | 31 | 36
2023 | 17 | 34 | 15 | 22 | 34 | 53 | 92
Notes: Our reach in the Darfur region and Khartoum compared to last year and compared to the target remains to be very low!
- We are only reaching 17% of the annual SAM target, hence behind by 83%

## Slide 9: New Admissions Trends in WN Refugee Camp
Chart: CAMPs SAM New Admission Jan- Jun (2022-2023)
| Jan-23 | Feb-23 | Mar-23 | Apr-23 | May-23 | Jun-23
2023 | 221 | 226 | 243 | 296 | 657 | 883
2022 | 113 | 174 | 129 | 251 | 457 | 544
UNHCR and MSF Spain started operating in Jul with additional number of nutrition promoters in July (slide from WN -SMOH). Refugee camp admissions trends in WN

## Slide 10: 2 a) Nutrition Sector Treatment Coverage Against Annual Target
PROGRAM | Target JAN 2023 | Revised Annual Target | Change in 2023 | % of Change |  | 7-mo Target (Jun- Dec 2023) | JAN 2023 % of Target vs PIN | May 2023 % of Target vs PIN | Reach up to Jun/Jul 2023) Against Annual Target
SAM OTP (6-59mo) | 456,007 | 559,446 | 103,439 | ↑ | 18.5% | 471,400 | 83% | 90.0%* | 140,741 (25.2%)
SAM SC (0-59mo) | 64,211 | 72,518 | 8,307 | ↑ | 11.5% | 42,302 | 70.0% | 70%** | 12,334 (17.0%)
TSFPs (6-59mo) | 1,211,977 | 1,374,160 | 162,183 | ↑ | 11.8% | 480,956 | 55% | 33%** | 76,323* (5.6%)
TSFPs (PLW) | 515,025 | 578,383 | 63,358 | ↑ | 11.0% | 202,434 | 55.0% | 33%** | 25,215* (4.4%)
e-BSFP for children 6-59 month | 101,936 | 418,666 | 316,730 | ↑ | 75.7% | 341,911 | 14.0% | 70%** | 
e-BSFP for PLW | 89,919 | 224,799 | 134,879 | ↑ | 60.0% | 183,585 | 23.0% | 70%** | 
Vitamin A | 5,917,508 | 5,917,508 | - |  | 0.0% | 5,917,508 | 85.0% | 85.0% | 
MYCN | 1,637,337 | 1,637,337 | - |  | 0.0% | 955,113 | 85.0% |  | 
*Based on annual program PINs
** Based on 7 months estimated PINs (May to Dec 2023)
Per reports collected so far, as actual will be higher than this, however couldn't received all reports

## Slide 11: 2 b) Sudan Sector Response Scenarios and Key Programme Shifts
For the first time, Sudan Nutrition sector response scenario was developed in discussion with sector partners, SAG and stakeholders
Response scenarios were categorized by:
  Hotspot areas:
    Front line/hotspot localities
    Darfur Region
    Kordofan Region
  States not directly affected by conflict: eastern and central states
  * Due to evolving situation, the strategy will be revised to reflect changes in population movement
Scenarios accounted for whether: (i) status-quo situation continues, or (ii) improvement in assess/security situation
Inclusion of critical sector response actions (from sector 2023 HRP activities)
Programmatic shifts and response modalities were contextualized for each region

## Slide 12: 2 c) National Guidelines on Simplified Approach for Management of Acute Wasting in U5
Updated guidelines for management of SAM without medical complications admitted in OTPs to be treated with RUTF until fully cured
Scale up of preventive community interventions including growth monitoring and mother support groups
Monitoring of cases of MAM in areas where TSFP services were unavailable
One of the main changes in the circular shared earlier in the year, restricting the use of RUTF supplies for management of SAM only even in areas where TSFP services were disrupted

## Slide 13: 2 d) Coordination with UNHCR in Sudan
Member of the Nutrition sector SAG and Nutrition sector partner
UNHCR update sector partners on weekly basis on the nutrition situation, responses and gaps in the camps
Sector coordination following up nutrition situation and responses in the refugees' camps
Sector coordination team visits refugee camps when on mission e.g. in White Nile
Sector organizes and advocates for dedicated or special meetings on responses in refugee camps as needed

## Slide 14: 2 e) Gaps in nutrition responses
Geographical coverage: 20% of SCs, 24% of OTP and 66% of TSFP not operational
Low coverage in IDP camps: e.g OTP: 45% in 11 camps and 48% in 93 camp like settings
Low coverage of preventive nutrition services (e.g BSFP, MNP, Vit A campaign)
Partial functionality of nutrition sites due to insecurity, limited access, and low staff
Delayed resumption of TSFP due to funding shortfall
Low reporting rate (OTP- only 70%, SC-53%)
Supplies stock out especially in the TSFP relative to other programmes
Limited supervision and monitoring especially in SMOH supported facilities
Inadequate staffing in the facilities
Limited analysis and triangulation of nutrition information and forecasting

## Slide 15
Aj Jazirah
Building Foundation for Development
Kuwait Patients Helping Fund
SMOH
Gedaref:
American Refugee Committee /Alight
CARE International in Sudan
Deutsche Welthungerhilfe e.V. (German Agro Action)
MedGlobal
Medical Teams International
SMOH
Kassala:
ALIGHT
American Refugee Committee /Alight
CARE International in Sudan
JASMAR Human Security Organization
Kuwait Patients Helping Fund
Plan International
Samaritan's Purse
SMOH
Sudanese Red Crescent Society
Khartoum:
Almanar Voluntary Organization
Life Support for Civilian War Victims ONG Onlus
Kuwait Patients Helping Fund
SMOH
Blue Nile:
Action Against Hunger
International Medical Corps
Relief International
Save the Children
SMOH
East Darfur:
ALIGHT
Almanar Voluntary Organization
American Refugee Committee /Alight
CARE International in Sudan
National Initiative Development Organization
SMOH
World Vision International
Central Darfur:
ACT Alliance / Norwegian Church Aid
Action Against Hunger
Catholic Relief Services
FUNDACION ACCION CONTRA EL HAMBRE SUDAN
International Medical Corps
Islamic Relief Worldwide
MSF
SAEKER VOLUNTARY ORGANIZATION
Save the Children
SMOH
World Relief
North Kordafan:
Islamic Relief Worldwide
SMOH
Northern:
SMOH
Northern
North Darfur
Red Sea
River Nile
North Kordofan
Gedaref
West Kordofan
South Darfur
Kassala
Sennar
South Kordofan
East Darfur
Blue Nile
White Nile
Aj Jazirah
Khartoum
Central Darfur
Abyei PCA
West Darfur
South Kordofan:
Action Against Hunger
Almanar Voluntary Organization
Concern Worldwide
GOAL
International Medical Corps
Islamic Relief Worldwide
Save the Children
SMOH
South Darfur:
ACT Alliance / Norwegian Church Aid
ALIGHT
American Refugee Committee /Alight
CARE International in Sudan
Life Support for Civilian War Victims ONG Onlus
International Medical Corps
Mercy Corps
National Initiative Development Organization
Rufaida Health Foundation
SMOH
World Vision International
Sennar:
Save the Children
SMOH
River Nile:
Building Foundation for Development
SMOH
Red Sea:
Life Support for Civilian War Victims ONG Onlus
Kuwait Patients Helping Fund
Save the Children
SMOH
Sudanese Red Crescent Society
West Kordofan:
Concern Worldwide
Islamic Relief Worldwide
SMOH
West Daruf:
Catholic Relief Services
Concern Worldwide
International Medical Corps
Save the Children
SMOH
Sudanese Red Crescent Society
World Relief
Partners Presence Pre-Conflict (April 2023):
North Darfur:
Auttash Organization for Peace and Developement
Deutsche Welthungerhilfe e.V. (German Agro Action)
GOAL
Kuwait Patients Helping Fund
National Plan Organization (NPO)
Relief International
Rural Development Network
SAHARI ORGANIZATION FOR DEVELOPMENT
Save the Children
SMOH
White Nile:
Action Against Hunger
Plan International
SMOH
40 Partners

## Slide 16
Northern
North Darfur
Red Sea
River Nile
North Kordofan
Gedaref
West Kordofan
South Darfur
Kassala
Sennar
South Kordofan
East Darfur
Blue Nile
White Nile
Aj Jazirah
Khartoum
Central Darfur
Abyei PCA
West Darfur
Partners Presence During Conflict (Jul 2023):
Aj Jazirah
International Rescue Committe
Premiere Urgence Internationale
Save the Children
Gedaref:
American Refugee Committee /Alight
CARE International in Sudan
International Rescue Committee
Medical Teams International
Premiere Urgence Internationale
Welthungerhilfe
Kassala:
ALIGHT
CARE International in Sudan
Plan International
Sudanese Red Crescent Society
Khartoum:
Almanar Voluntary Organization
International Rescue Committee
OVCI Ia Nostra Famiglia
Blue Nile:
Action Against Hunger
International Medical Corps
Medair
Relief International
Save the Children
IOM
East Darfur:
ALIGHT
Almanar Voluntary Organization
CARE International in Sudan
Central Darfur:
Action Against Hunger
Catholic Relief Services
International Medical Corps
Islamic Relief Worldwide
Save the Children
World Relief
North Kordafan:
Save the Children
South Kordofan:
Action Against Hunger
ALIMA
Almanar Voluntary Organization
Concern Worldwide
Save the Children
South Darfur:
ALIGHT
CARE International in Sudan
Mercy Corps
National Initiative Development Organization(NIDO)
River Nile:
Save the Children
Red Sea:
Save the Children
West Kordofan:
Almanar Voluntary Organization
Concern Worldwide
West Daruf:
Catholic Relief Services(CRS)
Concern Worldwide
Save the Children
Sudanese Red Crescent Society
World Relief
North Darfur:
ALIMA
Humanity for Development and Prosperity Int.(HDPO)
National Plan Organization (NPO)
Relief International (RI)
SAHARI Organization for Development
Save the Children
White Nile:
Action Against Hunger
Plan International
Save the Children
12 partners suspended services in some areas

## Slide 17: 3 a) Nutrition sector response: Partners presence
Response strategies:
Sustaining the existing services
Scaling up early detection and treatment
Scaling up prevention
Mass MUAC screening
Integration with other sectors
Programmatic shift in front line areas (can be done and what can be suspended)
Advocacy for special access in front line areas
Timely replenishment of supplies
Supporting nutrition staff with allowance/incentives
WFP

## Slide 18
Northern
North Darfur
Red Sea
River Nile
North Kordofan
Gedaref
West Kordofan
South Darfur
Kassala
South Kordofan
East Darfur
Blue Nile
White Nile
Aj Jazirah
Khartoum
Central Darfur
West Darfur
Abyei PCA
CARE, SMOH, WHO
SMOH, WHO
CARE, SMOH, WHO
AAH, RI, SMOH, WHO
SCI, SMOH, WHO
SMOH, WHO
AAH, IMC, SMOH, WHO
ALIGHT, SMOH, WHO
SMOH, WHO
ALIMA, RI, SMOH, WHO
ALIGHT, CARE, SMOH, WHO
AAH, CONCERN, SCI, SMOH, WHO
CONCERN, SMOH, WHO
CONCERN, SMOH, WHO
Sennar
AAH, SMOH, WHO
3 b) Response: Treatment of SAM with SAM with Medic Comp (SCs) – end of Jul 2023
SMOH, WHO
WHO, SMOH
SMOH, WHO
SMOH, WHO
Operational in the Area
Partially Operational
Stabilization centers:
According to 6 NGOs:
Total # reported: 21
  Operational: 15 (71.4%)
  Partially Operational: 3 (14.2%)
  Suspended: 3 (14.2%)
Capacity to Respond: 16 (76.1%)
Utilization: 12 (57.1%)
According to WHO (13 partners supporting 39 SCs currently :
As of 17th August
Total # reported: 160
  Operational: 100 (62.5%)
  Partially operational: 32 (20%)
  Suspended: 28 (17.5%)
Capacity to Respond:
  Need to mobilize additional capacity to respond: 130 (81.25%)
Reached:
Jan-Jul: 12,334
Apr-Jul: 6,683
SCs operational: 81%

## Slide 19
Northern
North Darfur
Red Sea
River Nile
North Kordofan
Gedaref
West Kordofan
South Darfur
Kassala
Sennar
South Kordofan
East Darfur
Blue Nile
White Nile
Aj Jazirah
Khartoum
Central Darfur
West Darfur
Abyei PCA
PI, SRCS(14,7), UNICEF
CARE, IRC, SCI, PUI, UNICEF
CARE, IRC, PUI, MTI, WELTHUNGERHILFR, UNICEF
AAH, IOM, IRC, IMC, SCI, RI, MEDAIR, UNICEF
SCI, UNICEF
UNICEF
AAH, CRS, IMC, SCI, IRW, WR, UNICEF
ALMANAR, CARE,NIDO, UNICEF
ALMANAR, IRC, OVCI, UNICEF
ALIMA, RI, SCI(14,7), HDPO, NPO, UNICEF
ALIGHT, CARE, NIDO, MERCY CORP, UNICEF
ALMANAR, ALIMA(2,3), AAH, CONCERN, SCI, UNICEF
CONCERN, CRS(5,5), SRCS(5,3), SCI, WR, UNICEF
CONCERN, ALMANAR, UNICEF
AAH, PI, SCI UNICEF
3 b) Response: Treatment of SAM without Medical Comp (OTP) – end of Jul 2023
Operational in the Area
Present but not Operational
OTPs:
According to 31 NGOs
Total # reported: 542
  Operational: 352 (64.9%)
  Partially Operational: 53 (9.8%)
  Suspended: 137 (25.3%)
Capacity to Respond: 389 (71.8%)
Utilization: 394 (72.7%)
SCI, SAHARI, UNICEF
MEDGLOBAL, UNICEF
SCI, UNICEF
UNICEF
Reached
Jan-Jul: 140,740 (77% RR)
Apr-Jul: 66,984
OTP functional 76%

## Slide 20
Northern
North Darfur
Red Sea
River Nile
North Kordofan
Gedaref
West Kordofan
South Darfur
Kassala
Sennar
South Kordofan
East Darfur
Blue Nile
White Nile
Aj Jazirah
Khartoum
Central Darfur
West Darfur
Abyei PCA
CARE, PI, WFP
AAH, IOM MEDAIR, WFP,RI
AAH, CRS, WFP, SCI
RI, HDPO, SAHARI, WFP
AAH, WFP, SCI
SCI,WFP
AAH, WFP
3 c) Response: Targeted Supplementary Feeding Program (TSFP) – end of Jul 2023
Operational in the Area
Present but not Operational
CARE, MTI, WELTHUNGERHILFE, WFP
TSFPs:
According to 16 NGOs
Total # Reported: 181
  Operational: 76 (14.0%)
  Partially Operational: 29 (5.4%)
  Suspended: 76 (14.0%)
Capacity to Respond: 87 (16.1%)
Limited Utilization: 99 (18.3%)
SCI, WFP
Reached: <5s
Jan- Jun: 76,323
Apr-Jun: 38,950
Reached: PLW
Jan-Jun: 25,215
Apr-Jun: 15,946
TSFP operational: 500
CARE, WFP
CARE, WFP
WFP
WFP
WFP

## Slide 21: Agenda 4a) Nutrition Sector Core Supply Update (as of 21st August 2023)
Supply | Available in country (ctns) | Expected/in pipeline (ctns) | Duration | Gaps (ctns) | Funding needed (US $) | Remarks
RUTF | 279,500 distributed and 44,000 in UNICEF central warehouse | 325,000 | Until end of Nov of 2023 | 139,000 | 12,510,000 | 12 states have supplies for 2 months. UNICEF is working on replenishing supplies by considering different route options.
F-100 | 899 distributed and 366 in UNICEF central warehouse | 2,125 | until the end of 2023. | 0 | 0 | 13 states have supplies for 1 to 2 months. UNICEF is working on replenishing supplies by considering different route options.
F-75 | 1,625 distributed and 540 in UNICEF central warehouse | 3,661 | until November of 2023 | 2,745 | 181,057 | 10 states have supplies for 1 to 2 months. UNICEF is working on replenishing supplies by considering different route options.
Types of Supplies | Number of beneficiaries to be reached in by end of 2023 | Available/In Pipeline | Duration (Time likely to last (mo) | Gaps in SAM Kits (coming 6 months) | Gaps in Funding (coming 6 months (US$)
SAM Kits (5 modules) | 64,200 SAM with Med Comp | 1,012 modules of SAM kits in country- under distribution 719 SAM Kits modules in pipeline | 1-2 months | 2,667 | 4.4 M
Operational Cost | 120 Stabilization Centers (excluding NGO supported) |  |  |  | 4.6 M
1,066 (SAM Kits-Modules) distributed during the crises Recent distribution: SAM Kits-modules distributed to Kassala, River Nile, Northern, Blue Nile, White Nile and Sennar |  |  |  |  | 

## Slide 22: 4b) Core supplies availability – NGO Partners Update (up to 31st July 2023)
14th May – 1st June: 1 NGO
1st – 14th June: 2 NGOs (3 States, 4 Localities)
15th – 30th June: 6 NGOs + SMOH + UNHCR (7 States, 13 localities)
1st – 15th July: 5 NGOs (9 States, 11 localities)
16th – 31st July: 4 NGOs (4 States, 7 localities). *7 of the 9 reported SCs were operational
SAM Kits Status |  |  | 
Bi-weekly Reporting Period | No. Stockout 0 Day | Stockout During the previous 14 days of reporting | Total # of SCs Reported
14th May – 1st June | 1 (100.0%) | 0 (0.0%) | 1
1st – 14th June | 4 (100.0%) | 0 (0.0%) | 4
15th – 30th June | 14 (100.0%) | 0 (0.0%) | 14
1st – 15th July | 11 (100.0%) | 0 (0.0%) | 11
16th – 31st July | 7 (100.0% | 0 (0.0%) | 7*
Therapeutic Milk (F-100/F-75) Status |  |  | 
Bi-weekly Reporting Period | No. Stockout 0 Day | Stockout During the previous 14 days of reporting | Total # of SCs Reported
14th May – 1st June | 1 (100.0%) | 0 (0.0%) | 1
1st – 14th June | 3 (75.0%) | 1 (25.0%) | 4
15th – 30th June | 14 (92.9%) | 1 (7.1%) | 14
1st – 15th July | 11 (100.0%) | 0 (0.0%) | 11
16th – 31st July | 7 (100.0% | 0 (0.0%) | 7*
Stabilization Centers (SCs)
Supply Status
Supplies at Warehouses: 3 SCs
Current stock to support services for:
  SAM Kits: 1 week to 3 months
  F-100/F-75: 2 weeks to 3 months

## Slide 23: 4b) Core supplies availability – NGO Partners Update (up to 31st July 2023)
14th May – 1st June: 5 NGOs (5 States, 9 Localities)
1st – 14th June: 11 NGOs (12 States, 14 Localities)
15th – 30th June: 16 NGOs + SMOH + UNHCR (13 States, 78 Localities)
1st – 15th July: 15 NGOs (11 States, 55 Localities) – Unknown supply status for 34 OTP sites
16th – 31st July: 17 NGOs (12 States, 56 Localities) – *Unknown supply status for 32 OTP sites and 7 MTs that were operational of total 312 OTP sites reported
RUTF Status |  |  | 
Bi-weekly Reporting Period | No. Stockout 0 Day | Stockout During the previous 14 days of reporting | Total # of OTP sites/MTs reported
14th May – 1st June | 17 | 11 | 28
1st – 14th June | 125 (90.6%) | 13 (9.4%) | 138
15th – 30th June | 238 (83.5%) | 47 (16.5%) | 285
1st – 15th July | 169 (81.3%) | 39 (18.7%) | 208
16th – 31st July | 135 (63.3%) | 78 (36.7%) | 213*
Outpatient Therapeutic feeding Program (OTP)
Reason for stockout
Challenge in transportation due to insecurity/poor road conditions
Increased admissions
Action Taken
Following up on supply delivery with SMOH/UNICEF
Current supply to support services for:
< 1 month: 46 OTP sites
1 -2 months: 61 OTP sites
> 2 months: 12 OTP sites
Unknown: 16 OTP sites
Stockouts in: BN, CD, ND, SK, WD, WK States

## Slide 24: 4b) Core supplies availability – NGO Partners Update (up to 31st July 2023)
14th May – 1st June: 3 NGOs (2 States, 6 Localities)
1st – 14th June: 4 NGOs (4 States, 14 Localities)
15th – 30 June: 4 NGOs (6 States, 17 Localities) – Including 9 TSFP sites supported by UNHCR + 4 NGOs (2 States, 7 Localities)
1st – 15th July: 8 NGOs (8 States, 35 Localities) – Unknown supply status in 32 TSFP sites
16th – 31st July: 11 NGOs (8 States, 20 Localities) – Unknown supply status in 16 TSFP sites. 95 TSFP sites were nonoperational out of 154 sites that reported
RUSF Status |  |  | 
Bi-weekly Reporting Period | No. Stockout 0 Day | Stockout During the previous 14 days of reporting | Total # of TSFP sites/MTs reported
14th May – 1st June | 3 (21.4%) | 11 (78.6%) | 14
1st – 14th June | 6 (18.2%) | 27 (81.8%) | 33
15th – 30th June | 19 (46.3%) | 22 (53.7%) | 41
1st – 15th July | 72 (82.8%) | 15 (17.2%) | 87
16th – 31st July | 7 (11.9%) | 52 (88.1%) | 59 (Incl 1 MT in IDP camp)
Targeted Supplementary Feeding programme (TSFP)
Reason for stockout
Stockout at state level
New FLA not yet signed
Action Taken
‘Implementation of revised Simplified Approach (i.e., management of SAM using RUTF until cured’
Current supply to support services for:
< 1 month: 2 TSFP sites
1 -2 months: 23 TSFP sites
> 2 months: 9 TSFP sites
Stockouts in: Aj Jazeera, CD, Gedaref, SK and WD States

## Slide 25: 5) Nutrition Sector Funding requirements 2023
Flagship programmes | Initial funding req HRP 12months US$ (Million) | Proposed Sector HRP Requirement (Jan-Dec) US$ (million)** | Revised and Final HRP May-Dec (7months) US$ (million ) | % change | Funding received in FTS (OCHA)* US$ (Million)
Overall funding requirements | 190.9 | 596 | 350.1 | ↑ 83.4% | 65.2 (18.6%)
Treatment of SAM SC (0-59mo) | 22.0 | 38.8 | 23.82 | ↑ 8.3% | 
Treatment of SAM OTP (6-59mo) | 62.7 | 139.86 | 117.85 | ↑ 88% | 
Treatment of MAM | 96.1 | 136.67 | 47.84 | ↓ 50.2% | 
Preventive interventions | 5.9 | 222.6 | 160.6 |  | 
*As of 21st August 2023
Urgent funding requirement for core supplies and operational cost
SAM in SC: US$ 5M SC Operational cost US$ 4.6 M
SAM in OTP: US$ 17.62M OTP Operational cost: US$ 137 M
TSFP: US$ 7M
** Not approved

## Slide 26: 6) Nutrition Sector capacity enhancement
Sector coordination
  Recruiting Roving Sub national coordinator to strengthen coordination at State level
Information management Officer (IMO)
  IMO support from SBP for since 20th July to 20th Sept
  IMO –TA for one year (under- recruitment)
Communication nutrition vulnerability in Sudan: Global Task Force on Sudan (in the making) to support analysis, prioritization, projection of situation
Capacity strengthening for partners and NIE: in discussion with the GNC

## Slide 27: 7) Challenges
Insecurity and limited access among partners to the affected areas
Delayed replenishing supplies in nutrition sites supported by both partners and the SMOH (need ad hoc modality of supporting delivering supplies to sites supported by SMOH)
Limited availability of cash among partners to support the ongoing activities
Difficulties in paying staff salaries/incentives by operational nutrition sector partners
Lack of allowances for the nutrition staff at site level. In some of states, 70% of the SMOH are working as volunteers as they have not been paid for several months
Increased operational costs to support the ongoing /new life saving nutrition services
Hiking of prices for basic needs (food, water, doubling of transportation costs etc)
Limited internet connectivity and mobile phones- presenting challenges to communicate with staff in the nutrition sites and reporting mechanisms
Replenishment of partners looted office equipment and assets in particular hotpots localities
Bureaucratic and access impediments (travel notifications, number of check points)
Dysfunction of nutrition information system - last update was in Feb 2023
Limited funding of the nutrition sector

## Slide 28: 8) Priorities for the coming period
Sustaining ongoing life saving nutrition services; SCs, OTP, TSFP and MYCN-IYCF-E
Scale up of nutrition timely detection and treatment as well as preventive interventions in both host and IDP camps
  Scale up of mass MUAC screening campaigns linked with health and nutrition activities
  Advocating for scale up of community prevention activities – nonfood interventions to overcome prevalent shortfall of nutrition supplies
Optimizing multi-sectoral integration and co-location of responses across the sectors that directly or indirectly impact the nutrition situation and responses (FSL, WASH, Health, Education, Protection etc)
Strengthening collection, monitoring analysis and projection of evolving nutrition and communication with stakeholders and guide 2024 sector response plan
2024 HNO and HRP
Strengthening coordination at state-level and government engagement
Strengthening coordination and collaboration with key humanitarian actors that are non-nutrition sector/cluster partners
Advocating for access and mobilizing for resources

## Slide 29
THANK YOU!
Notes: Insert map of the country with affected areas/districts or photos