## Workplan Template
This tool was developed by the Global Simplified Approaches Working Group. For other similar tools and resources, please visit www.simplifiedapproaches.org
Information below is pre-populated based on contents of checklist. Please modify to fit the context
Workplan Example: Simplified Approaches Implementation | Lead Organisation | Additional Partners | Month 1 | Month 2 | Month 3 | Month 4 | Month 5 | Month 6 | Month 7 | Month 8 | Month 9 | Month 10 | Month 11 | Month 12 | Month 13 | Month 14 | Month 15 | Month 16 | Month 17 | Status/Comments
Phase 1: Project Inception
Development of Concept Note/ToR for Project
Context analysis conducted (if necessary)
Consultation with Stakeholders
Consensus on protocol to be implemented
Identification of funding sources
Phase 2: Project Planning
Estimation of caseload and supply needs
Communications held with local authorities
Definition of Roles & responsibilities of all stakeholders
Implementation Plan developped, including; justification, objectives, protocol, operational plan & budget
Funding secured
Coordination mechanisms established at all levels (including technical steering committee)
Phase 3: Project Set-Up
Ethical submission & clearance (if necessary)
Partnership agreements finalised
Recruitment of project staff and set-up of teams
Training tools developped and training implemented
Phase 4: Project Implementation & Monitoring
Admissions start
Regular supervisions held
Coordination meetings at national and sub-national level
Mid-term results presented to technical committee
Phase 5: Project Finalisation & Reporting
Initial results presented at national level
Results submitted for publication
Policy conversations help for implementation of results at scale
Results shared internationally

## Logframe Template
|  | Description | Indicator | Means of Verification | Assumptions
Impact/Goal
Outcome | 1
Output | 1.1
Output | 1.2
Output | 1.3
Output | 1.4
Activities
Outcome | 2
Output | 2.1
Output | 2.2
Output | 2.3
Output | 2.4
Activities
Outcome | 3
Output | 3.1
Output | 3.2
Output | 3.3
Output | 3.4
Activities
Outcome | 4
Output | 4.1
Output | 4.2
Output | 4.3
Output | 4.4
Activities

## Budget Template
Budget Items | Quantity | Unit | Unit Cost | Year 1 $ | Year 2 $ | Year 3 $ | Total
Supplies | [6 empty] | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Human Resources | [6 empty] | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Contracts | [6 empty] | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Activities | [6 empty] | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Operational cost | [6 empty] | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
|  |  |  | 0 | 0 | 0 | 0
Total program |  |  |  | 0 | 0 | 0 | 0
Overhead
Grand total |  |  |  | 0 | 0 | 0 | 0

## Project Phases Infographic
Information in this sheet is automatically generated from the workplan sheet
Development of Concept Note/ToR for Project | Definition of Roles & responsibilities of all stakeholders | Ethical submission & clearance (if necessary) | Admissions start | Initial results presented at national level
Context analysis conducted (if necessary) | Implementation Plan developped, including; justification, objectives, protocol, operational plan & budget | Partnership agreements finalised | Regular supervisions held | Results submitted for publication
Consultation with Stakeholders | Funding secured | Recruitment of project staff and set-up of teams | Coordination meetings at national and sub-national level | Policy conversations help for implementation of results at scale
Consensus on protocol to be implemented | Coordination mechanisms established at all levels (including technical steering committee) | Training tools developped and training implemented | Mid-term results presented to technical committee | Results shared internationally
Identification of funding sources
Phase 1: Project Inception
Phase 2: Project Planning
Phase 3: Project Set-Up
Phase 4: Implementation & Monitoring
Phase 5: Finalisation & Reporting